## Slide 1
TSP Team Member Training, Module 7
Managing Your Work

## Slide 3: Topics
  Establishing a daily planning and tracking routine
    Time-on-task tracking
    Defect tracking
    Work size tracking
  Task management
  Task management issues
  Summary

## Slide 4: Context
Data
Project and Product Objectives
Product Versions
Plans
Refined Objectives
Phase or Cycle
TSP Launch or Re-launch
Postmortem
Analysis
Lessons Learned
Execute
Measure
Weekly Review

## Slide 5: Daily Team-Working Framework
Set priorities
Define task order
Execute
Track time
Mark task complete
Record defects found and fixed

## Slide 6: Topics
  Establishing a daily planning and tracking routine
    Time-on-task tracking
    Defect tracking
    Work size tracking
  Task management
  Task management issues
  Summary

## Slide 7: Time Management
Time management is very important in the TSP. Task time is
  one of the core measures used in the TSP
  used as part of other derived measures used in the TSP
To manage your time, you must
  track your time when working on a task
  update your available task time estimate when there are any changes (e.g., vacation, sick days, unanticipated schedule changes).

## Slide 8: Tracking Your Time
All activities that contribute to the value chain are listed as tasks in your plan.
Work against any task in your plan is timed.
  A time log is part of the TSP planning tool.
  When you begin work on a task, you start the timer in the TSP tool.
  When you stop work on a task, you stop the timer.
  The tool calculates durations automatically.
  If your task is interrupted, you can stop and then restart your timer to resume. Or you can enter the interruption duration time into a field within the TSP tool.
  If you forget to use your timer, you must estimate your time-on-task, and enter it manually.

## Slide 9: Earned Value is a Key Indicator of Task Progress
Earned value is used to help you understand whether you are progressing with your tasks at the rate you had planned.
Your personal EV and the team’s consolidated EV is reviewed each week during the team’s status meeting.
You must mark a task as completed in your plan so that you earn the value of the task.
When you mark a task completed, the TSP tool automatically updates your earned value.

## Slide 10: Task Management and Earned Value
Planned Value (PV)
PV for a task is an estimate of the work required to complete the task. It is expressed as the percent of the overall work required in your plan.
Earned Value (EV)
A task’s PV is earned when a task is completed. It must be entirely completed to earn the value.
Regardless of the actual effort required to complete the task, the earned value that is achieved is the value that was planned (i.e., the PV).
The cumulative EV is the total of the PV for all tasks that you have completed to date.

## Slide 11: Simple Example: Earned Value
30%
20%
30%
20%
10.5
30%
3
5
8
10
Cum. est. ef.
A
B
C
D
Task
3
2
3
2
Est. effort
PV
EV
Act. effort
1.3
20%
3.2
Cum. PV
30%
50%
80%
100%
Cum. EV
30%
50%
10.5
Cum. act. ef.
11.8
15.0
30%
80%
5.6
20.6
20%
100%

## Slide 12: Example – Cumulative EV
Cumulative PV
Percent Planned or Earned Value
Cumulative EV
What is the schedule status?

## Slide 13: Topics
  Establishing a daily planning and tracking routine
    Time-on-task tracking
    Defect tracking
    Work size tracking
  Task management
  Task management issues
  Summary

## Slide 14: Defect Tracking
Most defects are discovered during personal reviews, inspections, and other quality control activities.
Whenever a defect is found, you open the defect log of the TSP tool and record the following:
  the start time when defect was found
  defect type
  product or service that you are working on
  the process phase where the defect was injected
  the process phase where the defect was removed
  a brief description of the defect
  the stop time (when you have completed fixing the defect)

## Slide 15: Topics
  Establishing a daily planning and tracking routine
    Time-on-task tracking
    Defect tracking
    Work size tracking
  Task management
  Task management issues
  Summary

## Slide 16: Product Size Tracking
During the planning process, you estimated the size of the product or service that you will deliver.
When you have completed the product or service, you record its actual size.
Size is used to calculate many of the derived measures in TSP (e.g., defects per size).

## Slide 17: Topics
  Establishing a daily planning and tracking routine
    Time-on-task tracking
    Defect tracking
    Work size tracking
  Task management
  Task management issues
  Summary

## Slide 18: Task Management
  On most days, task management involves nothing more than
  opening the task plan and confirming task order for the day
  marking tasks complete as work is finished
  On some days, task management may also involve
  re-organizing tasks
  adding tasks
  deleting tasks
  merging tasks
  splitting tasks
  Change is inevitable, and the TSP planning process is dynamic to accommodate this reality.

## Slide 19: Dynamic Planning
The original plan developed during the launch is saved as the baseline plan.
However, changes inevitably occur due to a variety of reasons such as
  changes to requirements
  new insights into the work and the work processes
  overlooked task(s) during the launch
  risks emerge and must be mitigated
  team members added or removed from the team
  planning parameters change (task hours, other estimation parameters)

## Slide 20: Change Management
Changes to requirements must first be approved by management before they are addressed in your personal plan.
Whenever there is a candidate change to your plan
  confirm that you understand the rationale for the change
  analyze the impact that the change will have to your current commitments
  if the change is significant, communicate and coordinate with your team before modifying your plan
  If the change is modest, modify your plan; communicate the change through email or at the weekly status meeting
Communicate all changes to your plan.

## Slide 21: Organizing and Modifying Your Task List
Each morning, before you begin work on your tasks, open your personal plan. Examine your task list.
  Sequence tasks for the upcoming two weeks in the order that you plan to perform them.
  Ensure that completed tasks have been indicated as complete. Organize these appropriately.*
Add any new tasks to your plan.
If a task has been cancelled or shifted to one of your team members, then delete it from your plan.
Inform your team members when you have added or deleted tasks from your personal plan.
* Software tool dependent.

## Slide 22: Impact of Task Modification
The plan at the end of the launch is baselined. Subsequent to the launch, the plan will change based on a variety of reasons.
When you add, delete, or modify tasks, data in your plan will change. For example,
  planned hours
  planned value and earned value
  other measures that are derived from time-in-phase calculations
Changes to your plan will be reflected in the team’s plan during plan consolidation.

## Slide 23: Impact of Task Modification
The Baseline task hours represent the total number of estimated task hours when the plan was baselined during the launch.
The current plan hours represent the total number of estimated task hours in the current plan.
The % Change in this example shows that 101.3 – 88.3 = 13 hours were added since the plan was baselined at launch.
Example TSP Plan

## Slide 24: Sample – Planned and Actual Hours

## Slide 25: Topics
  Establishing a daily planning and tracking routine
    Time-on-task tracking
    Defect tracking
    Work size tracking
  Task management
  Task management issues
  Summary

## Slide 26: Task Management Issues: Parallel Tasks
Earned value is used to gauge your progress and the team’s progress.
You can only earn value for a task when it is completed.
When you are working on many tasks in parallel, earned value will be delayed until the parallel tasks are completed.
Likewise, if tasks are interdependent and cannot be closed until all are closed, then obtaining earned value will be delayed.
In these cases, the earned value indicator will not be as effective for helping you understand your progress.
Preferred task arrangement

## Slide 27: Task Management Issues: Task Size
When task size is too large, earning your planned value for the task will be delayed.
Break large tasks down into chunks so that the duration of any single task does not exceed your average weekly scheduled task hours.

## Slide 28: Indicator of Task Management Issues
Hours locked up in uncompleted tasks
= 24.8 – 2.1 = 24.7 hours
A general rule of thumb is that task hours for uncompleted tasks is less than one week’s worth of average task time.

## Slide 29: Task Management Issues: Getting Behind
During the launch, tasks are load balanced across the team to optimize the completion date for the project.
As work progresses after the launch, some team members may fall behind on their task list while others will complete tasks ahead of schedule.
When you are behind and need help, bring up the topic during the weekly team status meeting. This is where teamwork kicks in!
When tasks are transferred, the individual inheriting the task re-estimates the task using their personal data.

## Slide 30: Topics
  Establishing a daily planning and tracking routine
    Time-on-task tracking
    Defect tracking
    Work size tracking
  Task management
  Task management issues
  Summary

## Slide 31: Messages to Remember
As you begin your work after the launch, tracking time, defects, and actual product size must become routine.
Knowledge work is dynamic, and so your plan must be dynamic. Add and delete tasks to your plan when reality changes.
Be careful how your organize your tasks. Decompose them to a size where each task can be accomplished within a work week. That way, the earned value measure provides an accurate indicator of your schedule status.