## Slide 1
TSP Team Member Training, Module 6
The TSP Launch

## Slide 3: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 4: The TSP Launch
The purpose of the workshop is to launch the next cycle of your work effort.
During the launch, your team performs essential planning tasks that are part of your work.
The launch establishes a common and shared understanding of
  management’s goals for the project
  team and team members’ goals
  the work to be done
  processes that the team will use
  roles that the team members will perform
  the plan for doing the work
  the ongoing team communication process
  the management and customer reporting system

## Slide 5: The Launch Jump-Starts Team Building
Group of People
Team
Jellin'
The launch includes mechanisms that foster shared understanding of goals, roles, and how the team will work together.

## Slide 6: The Launch Process
1
Establish product and business goals
1
Assign roles and define team goals
2
Produce development strategy & process
3
Build overall and near-term plans
4
Develop the quality plan
5
Build individual & consolidated plans
6
Conduct risk assessment
7
Prepare management briefing & launch report
8
Hold management review
9
Launch postmortem
The launch is organized as a set of nine meetings and a postmortem.

## Slide 7: Inputs to the Launch
  Business needs
  Management goals
  Customer needs
  Trained resources
  Process assets
  Historical data

## Slide 8: Outputs From the Launch
  Team goals linked to management goals and customer needs
  Team role manager designations
  List of key requirements and deliverables
  Work strategy
  Size estimate for each deliverable
  Process description for each deliverable or service
  Task list and estimated effort for each task
  Schedule of available resources
  Earned value plan
  Quality plan
  Risk management plan
  Task owner designations
  An approved plan

## Slide 9: A Key Outcome of the Launch
Self-Managed Team
Team Lead

## Slide 10: Support During the Launch
A TSP coach guides the team through a defined process to develop its plan and to negotiate that plan with management.

## Slide 11: The Launch Notebook
In the launch workshop notebook are
  handouts for each launch meeting
    handout contents
    meeting agenda and meeting script
    launch scripts and forms
  planning, quality, and management briefing guidelines
  role, notebook, status, and summary specifications
  other forms and scripts
TSP Launch Notebook

## Slide 12: Launch Meeting Mechanics
Each meeting
is guided by an agenda
has defined meeting roles
is summarized in a meeting report
Role
Description
Chairperson
Facilitator / Timekeeper
Recorder
Arranges & leads the meeting
Keeps the team on track
Records all important decisions, actions & key information
Reviews and verifies recorded information at end of the meeting

## Slide 13: Recording the Launch Information
Much of the launch meeting information is typically captured on flipchart paper.
TSP Tool
Launch Meeting Record
But, then it is transcribed into the TSP tool or the launch meeting record.

## Slide 14: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 15: Meeting 1: Establishing Product & Business Goals
The first step in the TSP launch is for senior management and a marketing (or a customer) representative to tell the team
  what they want the team to do
  when the product is needed
  the resources available to the team
  the team’s flexibility
  why the job is important
  how management will measure success

## Slide 16: Prior to Meeting 1
Before the launch, preparation and participation guidelines are provided to executive management and marketing (or a customer representative).
Typically, the TSP coach will work with the presenters to ensure that the needed information is delivered during the meeting.

## Slide 17: Meeting 1 Agenda
TSP Launch Notebook
Process scripts guide the Meeting 1 agenda (as well as all subsequent launch meetings).
The agenda includes:
  selection of meeting roles (timekeeper, recorder)
  launch overview
  management presentation of business needs and goals for the team
  marketing or customer presentation
  Q & A to ensure team understanding of business goals and customer needs
Script LAU1

## Slide 18: The Presentations
Senior management
  describes the business context and goals
  identifies work constraints and where there is flexibility
  the requirements that are “must haves” vs. those that are “nice to have”
  defines how management will determine success
  responds to any questions the team has
Marketing or customer representative
  describes the product or service to be delivered by the team
  identifies the market niche or need that the product or service will fulfill
  compares and contrasts the product or service to alternatives already available
  responds to any questions the team has

## Slide 19: Active Listening By Team Members
Your personal filters, assumptions, judgments, and beliefs can distort what you hear.
As a listener, your role is to understand what is being said. This may require you to reflect what is being said and ask questions.
Reflect what has been said by paraphrasing. For example, great ways to reflect back would be
What I’m hearing is …
Sounds like you are saying …
Ask questions to clarify certain points.
Is this what you mean?
What do you mean when you say …

## Slide 20: Key Outcomes of Meeting 1
The key outcome of meeting 1 is that the team understands
  management goals and customer needs
  schedule and resource constraints
  areas of flexibility
  how success will be measured

## Slide 21: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 22: Meeting 2: Establishing Team Self-Management
During this meeting, the team
  Reviews and refines management goals into operational terms
  Adds team-specific goals
  Allocates team management roles so that each member has a role responsibility
Planning Manager
Quality Manager
Process Manager
Support Manager
Design Manager
Test Manager
Customer Interface Manager
Implementation Manager
The specific management roles will depend upon the type of work your team is doing.

## Slide 23: Meeting 2 Agenda
TSP Launch Notebook
The agenda includes:
  selection of meeting roles (timekeeper, recorder)
  reviewing and interpreting management’s goals and translating those into operational terms
  defining additional team goals
  identifying and discussing team management roles
  designating individuals who will perform the team management roles
Script LAU2

## Slide 24: Team Goal Setting
Discussing and agreeing to the team’s goals is the first step in becoming a jelled team.
  Discuss management’s goals to establish a common, shared view of what they mean.
  If a management goal still seems unclear, then you need to obtain clarification.
  State vague or implied goals in clear, operational terms.
  Do not identify too many goals. Identify one to three primary goals that will be closely tracked and managed; these are the really important ones.
  You must know when the goal has been met; therefore goals must be stated in measureable terms.
  Assign tracking responsibility to one or more team members
  You will review progress towards the goal(s) during the team’s future weekly meetings.

## Slide 25: Goals Are Recorded and Progress is Monitored
 |  | Measures |  | Tracking | 
Stakeholders | Goal | Target | Actual | Who | When

## Slide 26: Team-Member Roles
Team members are active participants in managing the project.
  The TSP roles cover all aspects of team management.
  When a role manager sees a problem that falls under their responsibility, they fix it.
  When team members see a problem, they alert the appropriate role manager.
  TSP roles help to focus the team on addressing its problems and establishing the plans and actions needed to accomplish the assigned mission.
  TSP team members feel responsible for the success of the team and take their role responsibilities seriously.

## Slide 27: The Roles
Planning Manager
Maintaining the team’s plans
Weekly reporting of team status
Supporting the team with any plan-related issues
The TSP tool guru
Quality Manager
Ensures that team members are recording their data
Helps team members follow the process for recording their data
Alerts team leader and team if any work is not of high quality
Ensures team’s processes and procedures are properly defined & used as defined
Encourages team members to submit process improvement proposals (PIPs) if they have problems or suggestions
Coordinates review and approval of PIPs
Process Manager

## Slide 28: The Roles, cont.
Support Manager
Ensures every team member has proper tools & support and knows how to use the materials
If needed, makes plans for development environment
Administers configuration management system
Design Manager
Responsible for the quality of team’s design work
Tracks design work & ensures that all design standards are being met
Ensures designs are being properly recorded
Customer Interface Manager
Responsible for team’s relationship with customer
Ensures customer requests are properly handled
Ensures every requested change is evaluated, planned, and approved before being implemented

## Slide 29: The Roles, cont.
Test Manager
Responsible for the quality of all the testing & test-related work including testing standards, test plans, test procedures
Ensures work is done in accordance with team’s and organization’s plans and standards
Responsible for overall quality of team’s implementation work
Concerned with adequacy of the design produced during design phase
Responsible for implementation standards & how they are followed
May be responsible for verifying the adequacy of unit test plans and completeness of unit test
Implementation Manager

## Slide 30: Other Team Management Roles
Other team management roles will be appropriate based on the nature of the project work. The team needs to discuss and decide upon the roles that are needed.
Other examples of team management roles
  Installation manager
  Security manager
  Safety manager
  Subcontract manager
  Performance manager
After the initial learning curve, the team management role typically takes about one hour per week.

## Slide 31: Team Member Role
Team members actually wear two hats.
They have a team management role that is designated during Meeting 2.
They have a team member role based on the specialized skills that they bring to the project.
Role
Manager
Team Member

## Slide 32: Expectations of the Team Member Role
Teams are successful when team members
  are skilled in their domain
  focus on doing their best work possible
  trust that teammates are doing their best work possible
  build personal plans that provide ongoing insight of their progress
  manage their commitments
  accept and perform a team role
  work to personally improve
  work to make the whole team better
  work through conflicts for the common good of the team
  are open and honest
Team Member

## Slide 33: Team Management Roles Are Recorded
 | Team Management Roles |  |  |  | 
Team Members | Planning | Process | Quality | Customer Interface | Support
Bill |  |  | 1 |  | 
Jim | 2 |  |  |  | 
Mary |  | 1 |  | 2 | 
Phil | 1 |  |  |  | 2
Susan |  | 2 |  | 1 | 
Ted |  |  | 2 |  | 1
Roles can be swapped during a long project.
1 = Primary role
2 = Backup role

## Slide 34: What About the Team Leader Role?
Except for very small teams, the team leader typically does not take one of the team management roles.
Sharing responsibility for team management allows the team leader to do their real job which is to
  set high standards
  motivate
  guide the work
  facilitate group problem-solving
  oversee the work

## Slide 35: Team Management Role: Report-Out
Individuals report out on their team management role during the team’s weekly status meeting.
  If you are unsure about what the specific expectations of the role are, then talk to your team leader and the TSP coach.
  Your team management role is a coordination role. It doesn’t mean you do all the work associated with your responsibility area. Get help from your team members.
  Throughout the effort, help your fellow team members in their management role by bringing relevant issues to their attention.
Communication is key!

## Slide 36: Time For An Exercise
This exercise, and upcoming launch meeting exercises, are based on a scenario of a team (of brothers and sisters) planning a large family reunion.
It just so happens that the brothers and sisters have undergone TSP training and since they want this to be a high-quality event, delivered on time, they intend to plan this work the TSP way!
You will be breaking out into groups and playing the roles of the brothers and sisters as they step through the launch meetings.
To get started, read the scenario description carefully.
We will then move on to the exercise.

## Slide 37: Meeting 2 Exercise: Define Team Goals and Roles
Read the instructions.
Complete the exercise in 30 minutes.
Be prepared to share your results.

## Slide 38: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 39: Meeting 3: Producing the Development Strategy
During this meeting, the team considers the effort from several perspectives and develops
  conceptual design with size estimates
  strategy for meeting the goals
  a list of support activities
  processes for conducting the work
TSP Launch Notebook
Script LAU3

## Slide 40: Conceptual Design Concept
?
Too big and abstract …
… so, break it down into pieces that can be understood.

## Slide 41: Example: Conceptual Design
Too big and abstract …
… so, break it down into pieces that can be understood.
Facility Condition Assessment Report
Energy efficiency analysis report
List of applicable tax and utility incentives
List of upgrade opportunities
LEED* facility report
Portfolio manager report
Cost segregation feasibility report
* LEED is Leadership in Energy and Environmental Design

## Slide 42: Don’t Be Confused …
When we discussed development of a conceptual design earlier in the course, the topic was personal planning.
Here, we are talking about a conceptual design of the team’s work.
An additional conceptual design is carried out, if needed, at the individual level during meeting 6* of the launch. Meeting 6 addresses your personal planning of the work that is assigned to you.
* Meeting 6 is Build Individual & Consolidated Plans.
You

## Slide 43: Sizing Each of the Parts
45 pages
60 slides
10 pages
65 pages
10 tables
20 diagrams
The team develops gross estimates of the sizes of the work and/or service parts of the effort.
This will help the team begin the effort estimation process. It can also help the team know whether the entire effort is feasible given schedule or other constraints.

## Slide 44: Meeting 3: Producing the Strategy
During this meeting, the team considers the effort from several perspectives and develops
  conceptual design with size estimates
  strategy for meeting the goals
  a list of support activities
  processes for conducting the work

## Slide 45: Strategy
In some cases, there are priorities to develop certain work products or services before others.
During this step of the meeting, the team arranges the products and services into work cycles.

## Slide 46: Strategy
Considerations for how a strategy is determined might include asking yourselves
  Are there dependencies among the product and service suite?
  Are there any products or services that need to be prototyped?
  Should we address high-risk areas first?
  Does the customer prefer to see certain products or services delivered before others are ready for delivery?

## Slide 47: Meeting 3: Producing the Development Strategy
During this meeting, the team considers the project from several perspectives and develops
  conceptual design with size estimates
  strategy for meeting the goals
  a list of support activities
  processes for conducting the work

## Slide 48: Support Required?
Consider the team’s support needs.
Additional tasks may be required to ensure the team has the right environment, tools, databases, etc., needed to complete their work.
Each support element is recorded.
The size of each element and effort required to obtain or produce each element is estimated.

## Slide 49: Meeting 3: Producing the Strategy
During this meeting, the team considers the effort from several perspectives and develops
  conceptual design with size estimates
  strategy for meeting the goals
  a list of support activities
  processes for conducting the work

## Slide 50: Characterizing the Work Processes
Having defined what needs to be done, the team is prepared to define how it will be done.
For each product or service, the team identifies the process they will use to do the work.
The team processes are based on the organization’s standard processes and the TSP.
The team produces a plan to develop any missing process elements.
These processes will provide the basis for deriving specific tasks required to do the work.

## Slide 51: Example: Document Development Process
Research & Analysis
Outline review
Draft
Personal review
Document inspection and editing
Document delivery
With the TSP, a personal review and an inspection (peer review) is always included in the product development process.

## Slide 52: Meeting 3 Exercise: Produce Development Strategy and Process
Read the instructions.
Complete the exercise in 50 minutes.
Be prepared to share your results.

## Slide 53: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 54: Meeting 4: Build the Overall and Near-Term Plans
During this meeting, the team works together to begin elaborating the plan by
  refining the work product or service sizes
  defining the tasks needed to complete the work
  estimating the effort for each task
  estimating available team task time for each week of the effort
TSP Launch Notebook
Script LAU4

## Slide 55: Refining the Work Product Sizes
During meeting 3, a conceptual design was developed and rough sizes were estimated for the work products and services. Other support elements were identified and also sized.
If the conceptual design is sufficiently detailed, then this step should be relatively straightforward.
Examine the size estimates for all of the products and services on the list and refine them if required.
If there is any serious disagreement about any estimate, the team takes the time to discuss it and to arrive at a consensus decision.

## Slide 56: Define the Tasks
During Meeting 3, the work processes were defined. The processes are now further elaborated into specific tasks for accomplishing the work.
Cycle 1
Cycle 2
Cycle 3
If multiple cycles are planned, then tasks are defined during the upcoming cycle at the task level. For future cycles, tasks are defined at a high level. They will be refined during relaunch before the cycle begins.

## Slide 57: Example: Define the Tasks
Develop content plan and obtain approval
Complete first draft of document
Conduct personal review
Conduct inspection
Conduct final editing
Obtain management approval & publish
Write annotated outline
Research and select design template for manuscript
Interview and select technical reviewers
Interview and recruit technical editor
Write plan and send to management
Phases
Tasks

## Slide 58: Estimate Time Needed and Time Available
Once the tasks have been defined, the effort required to complete each task is estimated.
Task Time Needed
Finally, the team estimates how much task time will be available during each week of the effort.
Task Time Available

## Slide 59: Meeting 4 Exercise: Build Overall and Near-Term Plans
Read the instructions.
Complete the exercise in 45 minutes.
Be prepared to share your results.

## Slide 60: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 61: Meeting 5: Developing the Quality Plan
With TSP, software quality is measured by counting defects injected and removed during the work process and normalizing those counts by the appropriate size measure.
During meeting 5, the team builds a quality plan that shows how the team will achieve its quality goal.

## Slide 62: Meeting 5: Develop the Quality Plan
During this meeting, the team develops a quality plan that estimates
  number of defects that will be injected per phase
  number of defects that will be removed per phase
  defect density of the final products and services
TSP Launch Notebook
Script LAU5

## Slide 63: Quality Planning
The quality-planning process actually started during meeting 2 when the team established its quality goals for the effort.
During meeting 5, the team translates those goals into meaningful operational terms.
To proceed, the team must resolve the following questions:
  What is a defect (in their work product or service)?
  How many defects do I typically inject into my work products or services?
  How many defects can we expect to be removed from work products or services during personal reviews, team inspection, or other quality control mechanisms?

## Slide 64: What is a Defect?
defect (noun)
a shortcoming, fault, or imperfection
lack or want, especially of something essential to perfection or completeness; deficiency
In TSP, a defect is anything that causes rework of your work product or service delivered after it has been completed.
By completed, we mean that the work product met the exit criteria of a process description.

## Slide 65
What is a defect in the context of your work?

## Slide 66: Estimating Defects Injected Per Phase
The team estimates the number of defects injected in each process phase.
To accomplish this, TSP quality planning uses defect injection rates.
When estimating defects injected, many teams just getting started with TSP will not have historical data. In these cases, the team should use their best judgment.
Once you begin collecting data, you will replace these judgment-based estimates with your own data.
Defects injected
hour

## Slide 67: Example: Estimating Defects Injected
Phase | Defects injected per hour
Planning | 0
Requirements specification | 1.5
Requirements review | 0
Requirements inspection | 0
Design | 2
Design review | 0
Design Inspection | 0
Implementation | 3
Product review | 0
Product inspection | 0
Pilot test | 0.25

## Slide 68: Estimating Defects Removed
Personal reviews, team inspections, and product testing are defect removal phases.
The TSP uses phase yield to estimate the defects removed within a phase.
Yield is the percentage of product defects that are removed in that phase.
In the TSP, we strive for high yields in our reviews and inspections before pilot test.
Phase | Defect removal phase?
Planning | 
Requirements specification | 
Requirements review | 
Requirements inspection | 
Design | 
Design review | 
Design Inspection | 
Implementation | 
Product review | 
Product inspection | 
Pilot test | 

## Slide 69: Examples: Phase Yield
A product contained 20 defects at the start of pilot testing and seven of those were found during testing.
Therefore, the pilot test yield is
A product contained 20 defects at the start of pilot testing and seven of those were found during testing and fixed. However, during the course of fixing an error, a new defect was injected.
Therefore, the pilot test yield is
Example 1
Example 2

## Slide 70: Example: Estimating Defects Removed
Phase | Phase yield
Planning | 0
Requirements specification | 0
Requirements review | 70%
Requirements inspection | 70%
Design | 0
Design review | 70%
Design Inspection | 70%
Implementation | 0
Product review | 70%
Product inspection | 70%
Pilot test | 60%

## Slide 71: Producing the Quality Plan
Once the defects injected have been estimated and entered into the tool, the tool calculates defects per size measure* (e.g., defects per document page) removed in each phase.
The team reviews and validates the quality plan.
  Do the displayed defect densities seem valid?
  Has sufficient time been allocated for personal reviews and inspections?
  Do the defects remaining (after pilot test) meet the quality goals?
If the quality goals are not met by the plan, the team needs to consider what it can do to make adjustments so that the goals are met (e.g., by setting stretch goals for yields and committing to careful, thorough personal reviews and inspections).
* The size measure selected will depend on the product or service and the size measure selected for that product or service by the team.

## Slide 72: Meeting 5 Exercise: Develop the Quality Plan
Read the instructions.
Complete the exercise in 25 minutes.
Be prepared to share your results.

## Slide 73: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 74: Meeting 6: Build Individual and Consolidated Plans
During this meeting, the team leader guides the team as tasks are allocated to team members.
  Team members select tasks that they are willing and able to handle.
  Individual team members develop their detailed plans.
  The planning manager leads the team through balancing and reviewing the final plan.
TSP Launch Notebook
Script LAU6

## Slide 75: Building Detailed Cycle Plans
Team-developed tasks (from meeting 4) for the current cycle are allocated to team members.
  Each individual adjusts their individual plan based on how they believe they can accomplish the task (using the TSP tool on their computer).
  The workload is balanced so that everyone completes their tasks at approximately the same time.
  After checking and validating their individual plan, the individual plans are consolidated to form the team plan.
Individual plan
Individual plan
Individual plan
Team plan

## Slide 76: Building Individual Plans
First, the team should agree on specific guidelines.
  Everyone needs to understand the mechanics of using the TSP planning tool.
  Naming conventions must be kept consistent.
In building their individual plans, each team member
  uses their own personal processes for assigned work (if different from team-specified process defined during meeting 3*)
  uses their own data to refine team-based task estimates
  ensures that the duration of each task is less than the total number of task hours available in a week; if not, then further decomposes tasks to meet this criterion
  estimates their individual task time for each week of the current cycle
  develops their earned-value plan
* Meeting 3 is Produce strategy & process.

## Slide 77: Consolidation of Personal Plans
Team plan
After individual plans are validated at the personal level, they are synchronized with the team plan.

## Slide 78: Team Review of Consolidated Plan
Once the Planning Manager has consolidated the individual plans, or the plans have been synchronized*, the team reviews the plan to ensure that the plan
  meets the team goals established during meeting 2 (assign roles and define team goals)
  meets the quality plan established during meeting 5 (develop the quality plan)
If the plan is in conflict with the goals, then
  Are additional resources needed?
  How would additional resources impact the plan?
  Can some tasks be scaled back without compromising quality?
The team must agree on a plan that will be presented to management.
* Consolidation method depends on the type of tool support being used.

## Slide 79: Meeting 6 Exercise: Build Individual and Consolidated Plans
You will work independently on this exercise.
Read the instructions.
Complete the exercise in 25 minutes.
Be prepared to share your results.

## Slide 80: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 81: Meeting 7: Conducting Risk Assessment
The team identifies and assesses the risks to the plan.
  The team leader leads the team through the risk identification process.
  Each risk is assessed for impact and likelihood.
  Mitigation plans are defined for high- and medium-priority risks.
  Each risk is assigned to a team member for monitoring and tracking.
Risks are tracked throughout the remainder of the effort. They are reviewed and reconsidered during the team’s weekly status meeting.
TSP Launch Notebook
Script LAU7

## Slide 82: The Approach
 | Step | Guidance
1 | Identify all risks | Use brainstorming to generate a list.
2 | Assign an impact to each risk | What is the impact to schedule, quality, cost, or functionality if the risk is realized? Assign a rating of high, medium or low to reflect impact.
3 | Estimate the likelihood of occurrence | For each risk, what is the probability that it will actually be realized as a problem? Assign a rating of high, medium or low to reflect the likelihood of the risk being realized.
4 | Assign tracking responsibility. | Each risk that is high-priority is assigned to a team member who will track it. High-priority is a risk that has been rated H-H, H-M, M-H, or M-M.
5 | Develop mitigations | For each high-priority risk, develop mitigation strategy. Add tasks to plan if necessary.

## Slide 83: Describing a Risk
Components of a Risk Statement
Condition A single phrase or sentence that briefly describes the key circumstances, situations, etc. causing concern, doubt, anxiety, or uncertainty.
Consequence A single phrase or sentence that describes the key, possible negative outcome(s) of the current situation.

## Slide 84: Risk Tracking
Risks are documented and tracked weekly.

## Slide 85: Meeting 7 Exercise: Conduct Risk Assessment
You will work independently on this exercise.
Read the instructions.
Complete the exercise in 20 minutes.
Be prepared to share your results.

## Slide 86: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 87: A Peek into a TSP Launch
We are about to watch a TSP team at the conclusion of a launch as the team leader presents alternative plans to management.
  The team determined that they could not meet all of management’s functionality and schedule goals.
  The team developed a set of alternative plans and is presenting them to management.
  Management must select a plan that best meets the business’s needs.

## Slide 88: Meeting 8: Prepare Management Briefing
The team prepares a presentation of their plan to management.
If the plan does not meet management’s goals, the team includes alternative plans. As examples, alterative plans might
  propose the addition of resources
  propose an alternative that meets the current schedule constraints but delivers a reduced-functionality version

## Slide 89: Meeting 8: Prepare Management Briefing
The coach
  reviews the objectives and procedures for the meeting
  explains the strategy/content for the management presentation
The team leader leads the team in planning the presentation for the management meeting. The team decides
  what material to present
  what material to include in any handouts
  who will deliver the presentation
  who will develop each item
  when to meet to assemble and review the presentation and handouts
TSP Launch Notebook
Script LAU8

## Slide 90: The Team’s Communication Objectives
The communication objectives for the team’s presentation are to
  articulate the plan clearly (both visually and orally) to facilitate management understanding
  demonstrate that the team has thoughtfully and thoroughly planned the effort
  convince management that the team is being responsive to the product and business goals that were highlighted by management during meeting 1 of the launch
  demonstrate that the team is committed to meeting the plan

## Slide 91: Preparing the Presentation
Some heuristics for preparing the presentation of the plan:
  Summarize the bottom line at the beginning of the presentation. Can the team satisfy the goals communicated during meeting 1? If not, what are the alternatives that are being proposed.
  Restate management’s goals to demonstrate the team’s understanding. Include any implied goals or team interpretation of goals that have been expressed in a quantified way.
  Briefly describe each product and/or service that will be delivered by the team.
  Use appropriate graphics to present the plan. Highlight milestone dates.
  If additional resources would improve performance against the goals, include a description of this impact.
  Include a summary of the quality plan and its positive impact with reducing rework and improving customer satisfaction.
  Present a summary of the high-priority risks. Describe the team’s mitigation plan for each risk.

## Slide 92: Preparing the Meeting Agenda
Meeting Section | Topics
Opening | Purpose of meeting and agenda review; assignment of meeting roles
 | Team member introductions
Body | Summary of TSP launch process
 | Management goals and team goals
 | Summary of products and/or services that the team will develop
 | Comparison of planning outcome to goals
 | The recommended plan Summary of products & services that the team will develop (include size) Quality plan summary Appropriate graphic that displays the plan (including key milestones)
 | Alternative plans (if appropriate)
 | Summary of high-priority risks
 | Q & A
Closing | Review of action items
 | Next steps

## Slide 93: Meeting 9: Hold Management Review
During launch meeting 9, the team delivers its presentation to management.
In response, management could
  approve the recommended plan
  approve an alternative plan
  require additional information before approving a plan
  request that the team consider a different alternative and replan
TSP Launch Notebook
Script LAU9

## Slide 94: Topics
Introduction
Meeting 1: Establish product and business goals
Meeting 2: Assign roles and define team goals
Meeting 3: Produce development strategy & process
Meeting 4: Build overall and near-term plans
Meeting 5: Develop the quality plan
Meeting 6: Build individual & consolidated plans
Meeting 7: Conduct risk assessment
Meeting 8: Prepare management briefing & launch report
Meeting 9: Hold management review
Launch postmortem

## Slide 95: The Launch Postmortem
The team meets after the launch to
  review the launch data and ensure that all information has been recorded accurately
  assign action for a team member to enter the launch materials into the team’s TSP repository
  suggest and consider improvements for the next launch and document the suggestions as process improvement proposals (PIPs)
  discuss and obtain agreement about the coaching plan
  complete the launch participant feedback forms for submittal to the Software Engineering Institute
TSP Launch Notebook
Script LAUPM

## Slide 96: Summary: The Launch Process
1
Establish product and business goals
1
Assign roles and define team goals
2
Produce development strategy & process
3
Build overall and near-term plans
4
Develop the quality plan
5
Build individual & consolidated plans
6
Conduct risk assessment
7
Prepare management briefing & launch report
8
Hold management review
9
Launch postmortem