## Slide 1
TSP Team Member Training, Module 4
TSP Planning Framework

## Slide 3: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 4
What value is there in producing plans?
Notes: Think of

## Slide 5: The Need for Plans
Businesses survive based on their ability to meet their commitments.
  Your customers need to understand the status of your work.
  Your managers need to understand the status of your work.
  When working on a team, co-workers need to understand the status of your work.
  To manage your personal commitments, you must understand the status of your work.
To accurately report on status, you must measure status.
To measure status, you must have measurable plans.

## Slide 6: TSP Planning Principles
Never make a commitment without a plan.
The people who do the work make the plan.
If you can’t plan accurately, plan often.
Plan what you know and plan at a level that fits the job.
If the plan doesn’t fit the work, revise the plan.
Base plans on historical data.
Historical data is most useful when you follow a consistent planning process.

## Slide 7: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
First, understand the requirements.
Decompose the problem into smaller work products or services.
Estimate the size of each of the work products or services.
Using size, estimate the effort required to develop each of the work products or services.
Identify the tasks needed to complete each work product or service.
Determine available effort hours and define milestone dates.

## Slide 8: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 9: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
First, understand the requirements.

## Slide 10: Define Requirements
Before a team can commit to do a job, its members must make a plan to meet that commitment.
The more information they can get about the commitment, the better.
However, if all you have is a simple one-sentence requirements statement, then you must either
  make a plan
  or
  tell management that the team cannot make a commitment until they know more about the job
The better the requirements are, the better the plan will be.

## Slide 11: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 12: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Decompose the problem into smaller work products or services.

## Slide 13: The Conceptual Design
A common planning approach is to take a big complex problem and then break it down into manageable parts.
During the conceptual design, you do just that.
  Start by developing a list of the smaller work products and/or services that you believe must be developed to address the overall requirements.
  Do not worry about detail. It should only take you an hour or so to develop the conceptual design.
  The purpose of the conceptual design is to support planning. Planning is cyclical (not linear) and the team will have opportunities to make revisions if necessary.
  Keep in mind that you will be sizing these smaller items during the next planning step.

## Slide 14: Conceptual Design Concept
?
Too big and abstract …
… so, break it down into pieces that can be understood.

## Slide 15: Example: Conceptual Design
Too big and abstract …
… so, break it down into pieces that can be understood.
Report: Cost-Benefit Analysis of Achieving LEED*
Methodology
Introduction
LEED credits
Executive summary
Conclusions
Results
Appendix
* LEED is Leadership in Energy and Environmental Design.

## Slide 16: Conceptual Design Will Improve Size Estimation Accuracy
An additional advantage of breaking down a big problem into smaller chunks is that your size estimation accuracy will actually increase as a result.
The reason accuracy increases is because there tends to be a balance between over-estimates and under-estimates of the smaller parts and the errors cancel out.
Under- estimates
Over- estimates

## Slide 17: Example: Size Estimation Accuracy
Scenario:
  Susan is an analyst and intends to estimate the size of a report that she is to develop.
  The format of the reports are typically the same and include the following sections.
    Introduction
    Methodology
    Results
    Discussion and Conclusions
  Susan has been doing this type of work for several years and has accumulated historical data of her estimation performance.

## Slide 18: Example: Size Estimation Accuracy
  She examined her historical data and noted the following:
    Actual sizes of the document sections have been within ± 50% of her estimates.
    There was an approximate balance between her over-estimates and under-estimates.
  Susan then developed the estimates for the report. She decided to try two methods for estimating and then compare the estimation error for each method.
Scenario (continued)

## Slide 19: Example: Size Estimation Accuracy
Estimation – Method 1
Using Method 1, the size of the entire document is estimated.
Susan estimated
Estimated
Total pages = 50
Doc Section |  | Number of pages
Introduction |  | 20
Methodology |  | 8
Results |  | 14
Discussion & Conclusions |  | 20
 | Total | 62
Estimation – Method 2
Using Method 2, the size of each of the parts is estimated.
Estimated

## Slide 20: Example: Size Estimation Accuracy
Estimation Error – Method 1
Estimated
Using Method 1, the size of the entire document was estimated.
Based on Susan’s estimation performance on past projects, the estimation range is
Error range = Total pages ± 50%
= 50 ± 25

## Slide 21: Example: Size Estimation Accuracy
Doc Section |  | Number of pages | Estimation error
Introduction |  | 20 | ± 10
Methodology |  | 8 | ± 4
Results |  | 14 | ± 7
Discussion & Conclusions |  | 20 | ± 10
 | Total | 84 | 
Estimated
Estimation Error – Method 2
Using Method 2, the size of the document sections were estimated.
Based on Susan’s estimation performance on past projects, the estimation error for each section (i.e., 50%) is shown in the table.

## Slide 22: Example: Size Estimation Accuracy
Estimation Error – Method 2, cont.
While the total size estimate (84 pages) is the sum of the individual estimates, the estimation error for the total is not the sum of the individual estimation errors.
The estimation error is the square root of the sum of the squares of the individual ranges.
Doc Section |  | Number of pages | Estimation error | (Estimation error)2
Introduction |  | 20 | ± 10 | 100
Methodology |  | 8 | ± 4 | 16
Results |  | 14 | ± 7 | 49
Discussion & Conclusions |  | 20 | ± 10 | 100
 | Total | 84 | - | 265

## Slide 23: Example: Size Estimation Accuracy
Comparing the estimation accuracy of each method
Estimation – Method 1
Estimation – Method 2
Error range = Total pages ± 50%
= 50 ± 25 pages
Error range = Total pages ± 50%
= 62 ± 16.3 pages
# Pages
0
10
20
40
60
80
90
100
30
50
70
Method 2
Method 1

## Slide 24: Summary: Produce Conceptual Design
The benefits of developing a conceptual design include
  it breaks down a big, abstract problem into small work products or services that can be intellectually managed
  it is easier to estimate the size of smaller, better-understood pieces of the puzzle
  size estimation accuracy improves significantly
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
In the next section, we explore estimation concepts in more detail.

## Slide 25: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 26: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Estimation

## Slide 27
What are some approaches to estimating how long it takes to develop a work product?
Notes: Think of

## Slide 28: Approaches to Estimating
Approaches to estimating include:
  Guessing
  Individual expert judgment
  Expert judgment by groups
  Using benchmark data
  Using your own historical data

## Slide 29
It is very difficult to make a vigorous, plausible, and job-risking defense of an estimate that is derived by no quantitative method, supported by little data, and certified chiefly by the hunches of managers.
- Fred Brooks
“
“

## Slide 30: TSP Approach to Effort Estimation
The TSP approach to estimation for planning is to use your own personal data to develop your estimates.
If you do not have any data, then use a different estimation method but begin to accumulate data for future planning.
In the TSP, the estimated size of a work product or service is used to estimate the effort (time) to develop it.
Therefore, in the context of planning, developing the size estimate is a means to an end because it is the effort estimate that we are after.

## Slide 31: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 32: The Effort Measure
In the TSP, the effort measure is task time.
Task time includes only that time that is directly expended on tasks that are listed in the team’s plan.
Task time is estimated and measured in minutes.
Task Time (min.)
Size

## Slide 33: Task Time and the Value Chain
A value chain is the set of tasks that are carried out to create value for the customer. These are the actual tasks that are part of the team’s plan.
Payroll time applies to both support activities and primary tasks.
Task time applies only to the primary tasks of a team’s value chain.
Energy efficiency report
Develop list of upgrades
Publish assessment
LEED feasibility report
Conduct peer review
Meetings – Email - Administrative
Human Resources
Training
Infrastructure
Support Activities
Primary Tasks

## Slide 34: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 35: Criteria for a Valid Size Measure
In the TSP, the size of a work product or service is used to estimate the effort (time) to develop it.
However, there are three important criteria that must be met to use this approach. The size measure must be
  useful for planning
  precise
  measurable

## Slide 36: Size Measure Must Be Useful for Planning
For a size measure to be useful for planning, it must correlate to development time.
Correlation implies that there is a relationship between two variables.
In this example, task time appears to increase as the size of the work product increases. Therefore, the size measure is useful for planning.
Time
Size

## Slide 37: Size Measure Must Be Precise
A size measure is precise if it has a specific and unambiguous operational definition.
When a size measure is precise, any two people who are measuring the item will obtain the same result.
Example
Size measure: Text lines (in a document)
Issues:
Is the title page included?
Are partial lines considered a line of text?
What about headers and footers?
Is a text line with only the page number on it counted?
Is an illustration caption a text line?

## Slide 38: Size Measure Must Be Measurable
A size measure must be observable and measurable. In most cases, this implies that it is directly observable and countable.
Examples
  pages
  paragraphs
  diagrams
  graphs
  lines of code
  requirement statements
Non-example
  themes (in a document or book)

## Slide 39: Exercise: Selecting Potential Size Measures
Read the instructions.
Complete the exercise in 10 minutes.
Be prepared to share your results.

## Slide 40: Selecting a Size Measure
To select a size measure:
Obtain historical data from past efforts that include work products or services similar to what you intend to develop.
Organize the product data by the level of effort (time) that was required to develop each product (highest effort to lowest effort).
Identify the product characteristics that could reasonably be considered as candidate size measures.
Determine if a candidate size measure is correlated to the effort that was used to develop the product.
  Create a graph with the candidate size measure along the horizontal axis and work effort (time) along the vertical axis.
  Plot each pair of historical data (candidate size measure, effort) as a point on the graph.
  If the data points are correlated, then the candidate size measure is related to effort and can be used for planning.

## Slide 41: Degrees of Correlation
Correlation is the degree to which two sets of data are related.
The correlation value, r, can be calculated based on the data values. The value varies between -1.0 and 1.0. The value, r2 is called the correlation coefficient.
r = 0.0
r = 1.0
r = -1.0
r = 0.73

## Slide 42: Required Correlation Level for Size Measure
In the TSP, a size measure can be used for planning if
r2 ≥ 0.5
Example
r2 = 0.61

## Slide 43: Example: Finding Correlation Using Excel
Product Size | Effort (hours)
163 | 15.0
765 | 69.9
141 | 6.5
166 | 22.4
137 | 28.4
355 | 65.9
136 | 19.4
1206 | 198.7
433 | 38.8
1130 | 138.2
y = 0.1402 x – 4.6037
r2 = 0.8988
Product size
Effort (hours)

## Slide 44: How to Find Correlation Using Excel - 1
Select the Scatter with only markers chart type.
Type in the two columns of values.
Select the two columns.
Select the Insert tab.
Select Scatter from the Charts ribbon area.

## Slide 45: How to Find Correlation Using Excel

## Slide 46: How to Find Correlation Using Excel
Select the Layout tab.
Select the chart.
Select More Trendline Options …
Select Trendline in the ribbon area.

## Slide 47: How to Find Correlation Using Excel
Select the options as shown in this dialog box.

## Slide 48: How to Find Correlation Using Excel
The Result

## Slide 49: If You Can’t Establish a Valid Size Measure
If you do not have sufficient historical data or are enable to establish a valid size measure, then you will need to use an alternative estimation method to estimate work effort
  Individual expert judgment
  Expert judgment by groups
  Using benchmark data
  Using your own historical data (whatever is available)
Continue to collect accurate data to build up your historical database.
In the future, you can reassess candidate size measures for their validity.

## Slide 50: Exercise: Selecting a Size Measure
Read the instructions.
Complete the exercise in 20 minutes.
Be prepared to share your results.

## Slide 51: Let’s Review
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
The purpose of the conceptual design is to divide up the problem space into work products and/or services that you can better comprehend.
The estimated size of the smaller pieces are used to estimate the effort required to develop them.
The size measure must be valid and task time is used as the effort estimate.

## Slide 52: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 53: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Estimate the size of each of the work products or services.

## Slide 54: Estimation Using a Relative Size Table
As you now know, partitioning a large work product or service into smaller, more manageable pieces leads to better size estimates.
In this section, you will learn a technique that will help you develop estimates more efficiently and effectively.
  The technique uses what is called a relative size table.
  The table organizes your historical size data into categories of types and size ranges.
  You can then refer to the table to quickly develop size estimates of your work products for your plan.
To illustrate the concept, consider how builders quickly estimate the square feet in a house that a buyer wants.

## Slide 55: The Builder’s Relative Size Table
 | Room Size (square feet) |  | 
Room Type | Small | Medium | Large
Den | 120 | 200 | 280
Living room | 220 | 300 | 400
Bedroom | 100 | 200 | 350
Kitchen | 110 | 185 | 265
Bathroom | 50 | 120 | 210
Dining Room | 115 | 195 | 275

## Slide 56: Developing the House Size Estimate
Room | Room type | Relative size | Estimated size
Master bedroom | Bedroom | Large | 350
Children bedroom | Bedroom | Medium | 200
Children bedroom | Bedroom | Medium | 200
Guest bedroom | Bedroom | Small | 100
Master bathroom | Bathroom | Large | 210
Children bathroom | Bathroom | Medium | 120
Guest bathroom | Bathroom | Medium | 120
Kitchen | Kitchen | Large | 265
Living room | Living room | Medium | 300
Family room | Living room | Large | 400
Dining room | Dining room | Medium | 195
Computer room | Den | Medium | 200
Power room | Bathroom | Small | 50
 |  | Total | 2710 sq. ft.

## Slide 57: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Using size, estimate the effort required to develop each of the work products or services.

## Slide 58: Estimating Effort
From past experience, the builder knows that his productivity is
13.4 sq. ft. per day
Estimated Effort:

## Slide 59: An Example: Estimating With Relative Size Table
A research analyst intends to conduct a survey. She would like to estimate the size and effort to develop a draft survey.
She has analyzed her data from past surveys and has confirmed that the number of questions in a survey is correlated to the effort required to complete a draft.
r2 = 0.67
# of survey questions
Effort (hours)

## Slide 60: An Example: Estimating With Relative Size Table
Data from her past survey work was used to construct this relative size table.
 | Survey Size (# of questions) |  | 
Survey question type | Small | Medium | Large
Personal info | 5 | 10 | 16
Demographic | 3 | 5 | 8
Subject matter | 10 | 25 | 40
Her past productivity data:
Survey item type | Questions per hour
Personal info | 35
Demographic | 43
Subject matter | 5

## Slide 61: Example, continued
Based on the requirements, the analyst believes that she will need the following for the survey:
Survey item type | Size | # of questions
Personal info | Medium | 10
Demographic | Large | 8
Subject matter | Medium | 25
To estimate effort, historical productivity values (from table on previous slide) are used to calculate effort for each section. The effort values for each section are are then summed to arrive at the total effort.
 | Size | # of questions | Questions/hr |  | Effort (hrs)
Personal info | Medium | 10 | 35 |  | 0.29
Demographic | Large | 8 | 43 |  | 0.19
Subject matter | Medium | 25 | 5 |  | 5.00
 |  |  |  | Total | 5.48

## Slide 62: Constructing a Relative Size Table
There are two methods for constructing a relative size table.
Linear Method
Used when you lack a sufficient amount of historical size data for the type of product you are producing.
(Number of product parts is less than 20.)
Statistical Method
Used after you have accumulated a sufficient amount of historical data for the type of product your are producing.
(Number of product parts is equal to or greater than 20)

## Slide 63: Linear Method: Constructing a Relative Size Table
A relative size table is constructed using historical data on the size of different parts that you have developed in the past.
From the data,
Calculate the mean of the product part sizes (
Identify the largest size product part (maximum).
Identify the smallest size product part (minimum).
Values of the relative size table:
Small
Medium
Large

## Slide 64: Example: Linear Method
Project # | Size (pages)
1 | 16
2 | 19
3 | 20
4 | 12
5 | 16
6 | 30
7 | 24
8 | 18
9 | 16
10 | 20
Small | Medium | Large
16 | 19 | 22

## Slide 65: Statistical Method: Constructing a Relative Size Table
A relative size table is constructed using historical data on the size of different parts that you have developed in the past.
From the data,
Calculate the mean (
Calculate the standard deviation ().
Values of the relative size table:
Very Small
Small
Medium
Large
Very large
M
S
VS
L
VL

## Slide 66: Example: Statistical Method
Project # | Size (pages)
1 | 16
2 | 19
3 | 20
4 | 12
5 | 16
6 | 30
7 | 24
8 | 18
9 | 16
10 | 20
11 | 34
12 | 22
13 | 40
14 | 12
15 | 36
16 | 27
17 | 27
18 | 22
19 | 18
20 | 16
21 | 33
Very Small | Small | Medium | Large | Very Large
7 | 15 | 23 | 31 | 39

## Slide 67: Exercise: Constructing a Relative Size Table
Read the instructions.
Complete the exercise in 15 minutes.
Be prepared to share your results.

## Slide 68: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 69: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Scheduling the tasks

## Slide 70: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Identify the tasks needed to complete each work product or service.

## Slide 71: How Are Products Developed?
A product is produced using a process.
A simple process can be broken down directly into a set of tasks.
Large processes are typically broken down into phases.
A process phase is then further broken down into a set of tasks.
Input
Product
Phase 1
Phase 2
Phase 3
Phase 4

## Slide 72
Test Case Development Process |  | 
Purpose: |  | To develop test cases.
Entry Criteria: |  | Product requirements, high-level design, detailed-level design, functional specifications (and/or use cases).
Step | Tasks | Description
1 | Define objectives | Determine the objectives of the test cases.
2 | Develop test descriptions | Provide test case titles and descriptions of each test to be performed. Include a mapping of the test case to the requirements, design elements, or specifications being validated by the test case.
3 | Specify initial conditions | Define initial conditions that must be met prior to the execution of each test case.
4 | Define procedures | Define the steps for each test case. For each step, describe eh action to be taken and the expected result.
5 | Review test cases | Review each test case using the review checklist Fix all defects found Record defects in defect log
6 | Inspect test cases | Inspect the test cases using the TSP inspection script (INS).
Exit Criteria: |  | Test cases are documented, reviewed, and inspected. Time and defect logs are completed. Process improvement proposals are logged.

## Slide 73: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Determine available effort hours and define milestone dates.

## Slide 74: Developing A Schedule
To develop a schedule, you need three things:
  a set of ordered tasks
  the estimated effort hours per task
  an estimate of available task hours per week
The schedule is developed by allocating your available task hours to the work that must be completed.

## Slide 75: Planning the Tasks
Define objectives
Develop test descriptions
Define initial conditions
Define the procedures
Review test cases
Inspect test cases
Assumptions:
There are four test cases.
The test cases have been sized.
Overall effort has been estimated.
Test Cases
Tasks
57 hours
Question:
Can you describe how this estimate was derived?

## Slide 76: Recall: The Relative Size Table Approach to Estimation
Data from his past work was used to construct this relative size table.
 | Test Case Size (# of test steps) |  | 
 | Small | Medium | Large
Test Case | 3 | 10 | 18
The size of each of the four test cases were estimated.
Test Case # | Size | # test steps
1 | Medium | 10
2 | Medium | 10
3 | Small | 3
4 | Medium | 10
 |  | Total 33
 | Test steps per hour
Productivity | 1.72
The size of each of the four test cases were estimated.
Estimated task time = 33 X 1.72 = 56.8 ≈ 57 hours

## Slide 77: Planning the Tasks
The effort estimate is distributed across the tasks based on historical data.
If data is unavailable, then use expert judgment.
Task |  | Percent | Effort estimate (task hours)
Define objectives |  | 11 | 6
Develop test descriptions |  | 19 | 11
Define initial conditions |  | 19 | 11
Define the procedures |  | 30 | 17
Review test cases |  | 11 | 6
Inspect test cases |  | 11 | 6
 | Total | 100 | 57 hours
The next step is to calculate the planned value for each task.

## Slide 78: Earned Value Management System
Planned Value (PV)
PV for a task is an estimate of the work required to complete the task. It is expressed as the percent of the overall work required in a work plan.
Earned Value (EV)
A task’s PV is earned when a task is completed. It must be entirely completed to earn the value.

## Slide 79: Planned Value
Task | Est. Effort task hours | Cumulative est. effort (task hours) | PV | Cumulative PV
Define objectives | 6 | 6 | 10.5 | 10.5
Develop test descriptions | 11 | 17 | 19.3 | 29.8
Define initial conditions | 11 | 28 | 19.3 | 49.1
Define the procedures | 17 | 45 | 29.8 | 78.9
Review test cases | 6 | 51 | 10.5 | 89.4
Inspect test cases | 6 | 57 | 10.5 | 100.0
Planned value (PV) for a task is an estimate of the work required to complete the task. It is expressed as the percent of the overall work required in a work plan.
For example, the total number of hours in the project above is 57 hours. The task, Define objectives, is estimated to be a six-hour task. Therefore, the planned value for this task is

## Slide 80: Developing the Schedule
To develop the task schedule, you must first estimate the task time per week that you will have available for working on the planned tasks.
For example, consider that you have estimated 15 hours of available task time per week to work on project tasks.
The plan week column records the week that a task is planned to be completed based on available task hours.
Week | Available task hrs | Cumulative avail. task hrs
1 | 15 | 15
2 | 15 | 30
3 | 15 | 45
4 | 15 | 60
Task | Est. Effort task hrs | Cum. est. task hrs | PV | Cum. PV | Plan week
Def. Objectives | 6 | 6 | 10.5 | 10.5 | 1
Dev. test desc. | 11 | 17 | 19.3 | 29.8 | 2
Def. inital. cond. | 11 | 28 | 19.3 | 49.1 | 3
Def. proc. | 17 | 45 | 29.8 | 78.9 | 3
Review | 6 | 51 | 10.5 | 89.4 | 4
Inspect | 6 | 57 | 10.5 | 100.0 | 4

## Slide 81: Earned Value
A task’s PV is earned when a task is completed.
The task must be entirely completed to earn the value.
Regardless of the actual effort required to complete the task, the earned value that is achieved is the value that was planned (i.e., the PV).
A project’s cumulative EV is the total of the PV for all project tasks that have been completed to date.

## Slide 82: Tracking the Schedule
Task | Est. Effort task hrs | Cum. est. task hrs | PV | Cum. PV | Plan week | Act. task hrs | Act. week | EV | Cum. EV
Def. Obj. | 6 | 6 | 10.5 | 10.5 | 1 |  |  |  | 
Dev. test desc. | 11 | 17 | 19.3 | 29.8 | 2 |  |  |  | 
Def. inital. cond. | 11 | 28 | 19.3 | 49.1 | 3 |  |  |  | 
Def. proc. | 17 | 45 | 29.8 | 78.9 | 3 |  |  |  | 
Review | 6 | 51 | 10.5 | 89.4 | 4 |  |  |  | 
Inspect | 6 | 57 | 10.5 | 100.0 | 4 |  |  |  | 
Once the project begins, actual task hours and earned value (EV) are closely tracked.
Tracked in real time

## Slide 83: Example: Tracking the Schedule
After two weeks, the work has taken longer than expected.
Task | Est. Effort task hrs | Cum. est. task hrs | PV | Cum. PV | Plan week | Act. task hrs | Act. week | EV | Cum. EV
Def. Obj. | 6 | 6 | 10.5 | 10.5 | 1 | 10.2 | 1 | 10.5 | 10.5
Dev. test desc. | 11 | 17 | 19.3 | 29.8 | 2 | 18.4 | 3 | 19.3 | 29.8
Def. inital. cond. | 11 | 28 | 19.3 | 49.1 | 3 | 0.5 |  |  | 
Def. proc. | 17 | 45 | 29.8 | 78.9 | 3 |  |  |  | 
Review | 6 | 51 | 10.5 | 89.4 | 4 |  |  |  | 
Inspect | 6 | 57 | 10.5 | 100.0 | 4 |  |  |  | 
Task | Est. Effort task hrs | Act. task hrs | Completed?
Def. Obj. | 6 | 10.2 | Yes
Dev. test desc. | 11 | 18.4 | Yes
Def. inital. cond. | 11 | 0.5 | No

## Slide 84: The Value Of Earned Value Method
The Earned Value method allows you to
  gauge how well you are performing with respect to schedule
  estimate project completion based on your current performance
In our example, the team member has earned 29.8 EV after three weeks.
Remaining EV
100 – 29.8 = 70.2 EV
EV rate
29.8 / 3 = 9.9 EV per week
Additional weeks
70.2 / 9.9 = 7.1 weeks
Total weeks to complete
2 + 7.1 = 9.1 weeks
Original completion projection
Week 4
# of weeks late
9.1 – 4 = 5.1 weeks late

## Slide 85: Exercise: Developing a Schedule
Read the instructions.
Complete the exercise in 20 minutes.
Be prepared to share your results.

## Slide 86: Module Topics
Overview: TSP Planning Process
Defining the requirements
Developing a conceptual design
Estimating size and effort
  Task time is used as the effort estimate
  Selecting a measure for product size
  TSP approach to estimation
Developing the project schedule
Summary

## Slide 87: The TSP Planning Process
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
First, understand the requirements.
Decompose the problem into smaller work products or services.
Estimate the size of each of the work products or services.
Using size, estimate the effort required to develop each of the work products or services.
Identify the tasks needed to complete each work product or service.
Determine available effort hours and define milestone dates.

## Slide 88: TSP Planning Framework
Define requirements
Produce conceptual design
Estimate size
Estimate effort
Determine tasks
Produce schedule
Develop product
Size database
Productivity database
Process phases
Resources available
Size, resource, & schedule data
Process analysis
Tracking reports
Work delivery
Customer need
Customer
Management
Legend
Items
Tasks