## Slide 1
TSP Team Member Training, Module 2
Overview of the TSP

## Slide 3: Topics
Knowledge work and the TSP
Key attributes of the TSP
  Self-managed teams
  Supportive environment
  Guidance provided by a defined process framework
  Mechanisms that foster congruent communication

## Slide 4: Knowledge Work
Knowledge work is the interpretation, development, and implementation of information by skilled professionals within a specific subject area.*
Knowledge work is both creative and complex.
Working on a team of knowledge workers is difficult because it requires everyone to
  process and debate abstract concepts
  integrate diverse parts into a working system
  wholeheartedly participate
  strive to do a superior job
* Drucker, Peter F. Management Challenges of the 21st Century. New York: Harper Business, 1999.

## Slide 5: Characteristics of Knowledge Work
The work is handcrafted so that a project’s outcome will depend on the skills, discipline, and commitment of those that develop it.
For efforts involving knowledge work
  All schedules are estimates; no one really knows when the work will be completed.
  Any work effort can get into trouble and no single person knows the exact best way to get out of trouble.
However … those doing the work know the most about the work.

## Slide 6: Managing Knowledge Work
The key principle in managing knowledge work is this: managers cannot manage it; the workers must manage it themselves.
To manage themselves, knowledge workers must
  be motivated
  make accurate plans
  negotiate commitments
  measure their work
  track their plans
  deliver quality products in alignment with their plans
The Team Software Process (TSP) shows individuals how to perform these skills as self-managed teams.
Watts Humphrey Creator of the TSP
Notes: Watts Humphrey pointed out that for knowledge workers to manage themselves, they must know how to manage. That is the fundamental reason for the extensive focus on management topics in PSP training.

## Slide 7: What’s In a Name?
The Team Software Process was initially developed to address knowledge work involving the development of software. Hence, its name.
However, the TSP approach is entirely applicable to other types of knowledge-based work.
“A rose by any other name
would smell as sweet.”
- William Shakespeare
Notes: This quote from Shakespeare is meenat to say that the names of things do not matter, only what things are.

## Slide 8: The “T” in TSP
The TSP was designed for groups of people that
  are working together towards a common goal
  work on interdependent tasks
  depend on and support each other
The TSP approach includes strategies that promote successful team-building.
  All team members are trained to use the same methods for planning, tracking, and managing their work.
  Mechanisms are put in place that foster common understanding of team goals, roles, and work processes.
  Analysis techniques are used to manage the work to a successful conclusion.

## Slide 9: Topics
Knowledge work and the TSP
Key attributes of the TSP
  Self-managed teams
  Supportive environment
  Guidance provided by a defined process framework
  Mechanisms that foster congruent communication

## Slide 10: Team Management Models
Project Manager
Development Staff
TSP Coach
Traditional Project
TSP Self-Managed Team
The PM plans, directs, and tracks the work.
The Team directs, and tracks the work.
Team Lead

## Slide 11: Management Activities Are Shared
TSP Coach
Team Lead
Leads, motivates, and protects the team. Represents team to management.
Customer Interface Manager
Coordinates with customer and/or stakeholders. Keeps communication channels open and active.
Planning Manager
Tracks the team’s plan
On the lookout for schedule and commitment course corrections.
Quality Manager
Tracks the team’s quality plan. Alerts team when there are quality issues.
Other team management roles assigned on as-needed basis.
Process Manager
Ensures that team’s processes are properly defined and used. Coordinates process change requests.

## Slide 12: Team Member Management Roles
Each team member takes on one of the team’s management roles.
The team discusses and establishes the roles. Then, team members select their own role.
Roles can be swapped during the project when project re-planning occurs.
After an initial learning curve, the role responsibilities for each team member should not take longer than 1-2 hours per week.
The team management role is typically a coordination role. Other team members can help to implement specific actions that may result from recommendations that have been discussed and approved by the team.

## Slide 13: The Team Leader’s Role
Except for small teams, the team leader does not take one of the other team management roles.
The team leader’s responsibilities are to
  guide the team in doing their work
  provide management support
  establish and maintain high standards for the work
  make the team accountable for problem solving
  support the self-directed management concept
The shared management concept allows the team leader to focus on the things that a team leader should be focusing on.

## Slide 14: Topics
Knowledge work and the TSP
Key attributes of the TSP
  Self-managed teams
  Supportive environment
  Guidance provided by a defined process and measurement framework
  Mechanisms that foster congruent communication

## Slide 15: Team Members Support Each Other
The characteristics of a self-managed team are that members
  have a sense of membership and belonging
  are committed to a common goal
  own the process and plan
  have the skill to plan and the discipline to follow their plan
  are dedicated to excellence
When teams are trained in the TSP, they know how to manage themselves. They
  meet their commitments
  are more productive
  produce higher quality products at lower cost

## Slide 16: The TSP Coach
TSP Coach

## Slide 17: The TSP Coaching Role
The coach
  is an SEI-trained and certified TSP coach
  provides training and facilitates the adoption of TSP
  works with the team leader to build the team
  is an objective observer that guides the team
  uses data to ensure that the process is meeting organizational objectives
Tiger Woods and his coach Hank Haney

## Slide 18: Training Support
All members of a team are trained in the TSP.
Personal Software Process (PSP) Training
TSP Team Member Training
Leading a Development Team
TSP Executive Strategy Seminar

## Slide 19: Tool Support
TSP Excel Tool
Process Dashboard

## Slide 20: Books To Support Learning

## Slide 21: Technical Reports, Presentations, Articles

## Slide 22: Topics
Knowledge work and the TSP
Key attributes of the TSP
  Self-managed teams
  Supportive environment
  Guidance provided by a defined process and measurement framework
  Mechanisms that foster congruent communication

## Slide 23: TSP Process Elements
Process scripts
Provides guidance on how to use a TSP process.
Measurements
Defined measures that provide helpful feedback about performance.
Forms
Provides consistency for data collection activities.
Standards
Operational definitions to support uniform implementation.

## Slide 24: Topics
Knowledge work and the TSP
Key attributes of the TSP
  Self-managed teams
  Supportive environment
  Guidance provided by a defined process framework
  Mechanisms that foster congruent communication

## Slide 25: TSP Mechanisms that Foster Team Effectiveness
Team Launch
Daily planning and real-time tracking
Weekly team meetings
Reporting to management
Post mortem

## Slide 26: The TSP Launch
A TSP launch is a multi-day workshop that builds the team and guides the team through planning a project.
During the launch the entire team works together to establish a common and shared understanding of
  management’s goals for the project
  team and team members’ goals
  development work to be done
  processes that the team will use
  roles that the team members will perform
  plan for doing the work
  the ongoing team communication process
  management and customer reporting system

## Slide 27: The Launch Process
1
Establish product and business goals
1
Assign roles and define team goals
2
Produce development strategy & process
3
Build overall and near-term plans
4
Develop the quality plan
5
Build individual & consolidated plans
6
Conduct risk assessment
7
Prepare management briefing & launch report
8
Hold management review
9
Launch postmortem
The launch is organized as a set of nine meetings and a postmortem.

## Slide 28: The Launch Notebook
In the launch workshop notebook are
  handouts for each launch meeting
    handout contents
    meeting agenda and meeting script
    launch scripts and forms
  planning, quality, and management briefing guidelines
  role, notebook, status, and summary specifications
  forms, and scripts
TSP Launch Notebook

## Slide 29: Coach Role
A TSP coach guides the team
through a defined process to develop
its plan and to negotiate that plan with
management.

## Slide 30: Launch Meeting Mechanics
Each meeting
is guided by an agenda
has defined meeting roles
is summarized in a meeting report
Role
Description
Meeting leader
Facilitator
Recorder
Arranges & leads the meeting
Keeps the team on track
Records all important decisions, actions & key information
Reviews and verifies recorded information at end of the meeting

## Slide 31: Recording the Launch Information
The Plan
Launch Meeting Record

## Slide 32: Incremental Planning
Large projects are planned incrementally. During the initial launch
  near-term tasks are planned in detail
  distant tasks are planned at a higher-level
Cycle 1
Launch

## Slide 33: Future Planning Cycles are Preceded by a Relaunch
Cycle 1
Cycle 2
Cycle 3
Launch
Relaunch
Relaunch
Completed
A relaunch also occurs when there are substantive changes to the plan or when new members are added to the team.

## Slide 34: The Relaunch Process
1
Establish product and business goals
1
Assign roles and define team goals
2
Produce development strategy & process
3
Build overall and near-term plans
4
Develop the quality plan
5
Build individual & consolidated plans
6
Conduct risk assessment
7
Prepare management briefing & launch report
8
Hold management review
9
Launch postmortem
If the commitment to management is unchanged, then there is no need for the management meetings.

## Slide 35: Products of the Launch or Relaunch
During the launch workshop, the team produces a comprehensive plan for their work that includes
  team goals
  team role assignments
  development strategy and incremental build plan (if needed)
  processes for developing the products or services
  overall project plan
  next-phase detailed plan including balanced work assignments
  quality plan
  individual team member plans
  consolidated team member plan
  risk assessment and mitigation plan

## Slide 36: TSP Mechanisms that Foster Team Effectiveness
Team Launch
Daily planning and real-time tracking
Weekly team meetings
Reporting to management
Post mortem

## Slide 37: Daily Planning and Real-Time Tracking
After the launch
  Each team member controls their work from their personal plan.
  Team members begin each day by reviewing their personal plan and making any small alterations based on changes or shifting priorities.
  During the day, each team member tracks time-on-task in real time.
  Team member performance results are consolidated automatically in the team plan.
Team plan

## Slide 38: TSP Commitment Tracking
Each team member is responsible for
  gathering data on their work
  ensuring the quality of the work that they produce
  tracking status against their personal plan
  keeping the team informed of their status
TSP Measure | Description
Size | Size of the work.
Task time | Recorded in minutes per task.
Defects | Defects injected and removed per phase.
Schedule status | Using earned value.

## Slide 39: TSP Mechanisms that Foster Team Effectiveness
Team Launch
Daily planning and real-time tracking
Weekly team meetings
Reporting to management
Post mortem
Re-launch

## Slide 40: The Weekly Team Meeting
The weekly team meeting is one of the most important parts of the TSP process.
The TSP prescribes a defined meeting agenda that includes
  Team lead report
  Team member management role report
  Review of team goals and team risks
  Team member progress and status
  Next week plans
Some TSP teams also include a brief daily stand-up meeting to keep members focused on high-priority tasks and to arrange peer support.

## Slide 41: TSP Mechanisms that Foster Team Effectiveness
Team Launch
Daily planning and real-time tracking
Weekly team meetings
Reporting to management
Post mortem
Re-launch

## Slide 42: Reporting to Management
Management’s role is to
establish business and product objectives, success criteria
negotiate and approve plans
monitor progress
motivate proper use of data by management team
reward quality and success

## Slide 43: Status Reporting Frequency
Weekly for the team lead’s direct management
Monthly for upper-level management*
General Guidelines for TSP Teams
* However, policies differ based on upper-level management preferences.

## Slide 44: What Information Does Management Need?
Report summary
Current status
Completion projections
Next steps

## Slide 45: TSP Teams Use Data To Report Status

## Slide 46: TSP Mechanisms that Foster Team Effectiveness
Team Launch
Daily planning and real-time tracking
Weekly team meetings
Reporting to management
Postmortem

## Slide 47: Postmortems Conducted After Each Phase
TSP teams hold a postmortem right before they relaunch the next cycle or phase of the project.
The postmortem provides the data teams need to capitalize on their experiences and improve their project performance.
Phase 1
Phase 2
Phase 3
Postmortem
Postmortem
Postmortem
Launch
Relaunch
Relaunch

## Slide 48: The Coach Role
Responsibility for growth in capability
Responsibility for team results
x
Coach

## Slide 49: Let’s Get Better
During the postmortem
  performance data is consolidated and analyzed
  lessons learned are chronicled while the team members’ experiences are fresh
  estimation parameters are updated based on actual performance from the previous phase
  process improvements are discussed and agreed upon

## Slide 50
The benefit and value of measurement comes from the decisions and actions taken in response to analysis of the data … not from the collection of the data.
17.5%
2569
54
65%
17.5%
2569
54
65%
17.5%
2569
54
65%
Data Collection
Postmortem
Decision making

## Slide 51: The Glue That Binds It All Together
Successful high-performance teams are composed of members who are committed to the concept of process discipline.
  All team members understand the reasons for their task assignments and feel responsible for following their defined processes and plans.
  Personal commitments are thoughtfully considered before the commitment is made.
  When team members see something that needs changed or fixed, they make the changes themselves or raise the issue to a suitable level of management.
T S P

## Slide 52: Messages to Remember
Knowledge workers perform most effectively when they manage their own work.
Teams will underperform if team structure, process, and environment are not explicitly addressed in meaningful ways.
The TSP includes mechanisms that accelerate the path to high performance. These include
  a defined team launch to support effective team building and the development of a comprehensive project plan
  defined processes
  daily plan tracking and real-time data collection
  effective communication mechanisms including the weekly meeting, daily stand-ups, and management reporting
  formalized postmortem events to promote process improvement and organizational learning