## Slide 1
TSP Team Member Training, Module 8
The Weekly Status Meeting

## Slide 3: Topics
Introduction
Schedule status indicators

## Slide 4: A Peek into a TSP Weekly Meeting
We are about to watch a TSP team conduct part of their weekly meeting.
  The team is composed of four team members, a team leader and a TSP coach.
  The team developed their plan and started work seven weeks ago.
  The team is meeting weekly to discuss the status against their plan and to manage the quality of their product.
After we watch the video, we will have a class discussion about how the teams in your organization plan and manage their work.

## Slide 5
How similar or dissimilar are your organization’s team meeting practices?
Notes: Think of

## Slide 6: The TSP Weekly Meeting
The team we watched in the video
  creates detailed plans that all team members are committed to
  gathers complete, consistent, and accurate data
  tracks the status of its plan on a weekly basis and takes responsibility for schedule problems
  regularly conducts load balancing to ensure an optimized schedule with respect to time-to-delivery
  reviews the quality of its product weekly and is accountable for building a superior product

## Slide 7: Key Communication Event
The weekly status meeting is an important part of the TSP. During the team meeting
  the team leader communicates the management perspective to the team
  each team role manager reports out on any activities in their area of responsibility
  team performance status is reviewed
  individual team member status is shared
  project goals, risks, and issues are reviewed and assessed
The weekly status meeting is intended to be efficient and concise.
  Share status for understanding but avoid problem-solving.
  Identify actions and/or schedule a different meeting to address complex issues that involves problem-solving.
The TSP script, WEEK, provides guidance for conducting the weekly status meeting.

## Slide 8: Before the Meeting Begins …
Each team member must be prepared for the team meeting.
  Review your plan to ensure that it is accurate and up to date.
  Be ready to concisely share your status.
  Jot down a list of any concerns or issues that you believe should be brought to the team’s attention. Are there new risks that you want to highlight for the team?
  Be ready to describe what your tasks will be over the next two weeks. If there are dependencies associated with these tasks, be ready to identify those at the meeting.
  Are you responsible for tracking any of the team’s goals or team risks? If so, be ready to provide a status on those.
  Be ready to concisely report on topics related to your role function.

## Slide 9: Where Are We?
Throughout the project, a primary question facing the team is:
Will the team be able to meet its committed date?
To answer this question, consider the following:
  Does the team’s current plan meet the committed completion date?
  What is the status of the team’s tasks against the current plan?
  If the current plan does not meet the committed completion date, what is the projected completion date?

## Slide 10: Tracking Status
How precisely should we track our work?
If you cannot recognize a one-day slip, you can only take action when the delay is obvious.
But, by then, it is usually too late to recover.
With the TSP, one-day schedule slips can be detected.
“…schedule slips, one day at a time.”
- Fred Brooks in The Mythical Man Month

## Slide 11: Planning is Dynamic
The work is dynamic. Therefore, the plan must be dynamic.
As the team identifies additional work that was not initially envisioned during the launch, these tasks are added to the plan.
Therefore, the team needs to constantly monitor the plan to understand the status of the project with respect to the committed completion date.
There are a number of measures used in TSP that support the team so that they have up-to-date knowledge of schedule status.
TSP software tools support the team in developing, monitoring, and managing your TSP plan. Examples include
  TSP Excel Tool
  Process Dashboard
  Other proprietary applications

## Slide 12: The TSP Project Plan Summary
Different TSP support tools may have a dissimilar “look-and-feel,” but they all collect and report the same type of information.
After the project commences, the TSP support tool reports team performance comparing performance estimates to actuals.
Key performance indicators are reported in the tool’s project plan summary so that you (or any team member) can understand the team’s status at any time during the project.

## Slide 13: Topics
Introduction
Schedule status indicators

## Slide 14: Schedule Status Indicators
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
In this section, we will explore a number of indicators to help you understand the status of your project.

## Slide 15: What is the Earned Value Method?
You need a way to track and report progress. The challenge is that
  most projects have many tasks of differing types and sizes
  tasks are completed in a different order than originally planned
The Earned Value (EV) method provides a convenient way to address this tracking and reporting problem.
  The EV method establishes a value for every task, regardless of its type.
  Whenever you complete a task, regardless of its type, you earn this EV amount.
  To judge progress against the plan, compare the EV each week with the planned value (PV) for that week.

## Slide 16: TSP Earned Value Method
Planned Value (PV)
PV for a task is an estimate of the work required to complete the task. It is expressed as the percent of the overall work required in a project plan.
Earned Value (EV)
A task’s PV is earned when a task is completed. It must be entirely completed to earn the value.
Regardless of the actual effort required to complete the task, the earned value that is achieved is the value that was planned (i.e., the PV).
A project’s cumulative EV is the total of the PV for all project tasks that have been completed to date.

## Slide 17: Simple Example: Earned Value
30%
20%
30%
20%
10.5
30%
3
5
8
10
Cum. est. ef.
A
B
C
D
Task
3
2
3
2
Est. effort
PV
EV
Act. effort
1.3
20%
3.2
Cum. PV
30%
50%
80%
100%
Cum. EV
30%
50%
10.5
Cum. act. ef.
11.8
15.0
30%
80%
5.6
20.6
20%
100%

## Slide 18: Using EV Method to Determine Schedule Status
To determine a project’s current schedule status, compare the current cumulative EV to the planned cumulative PV.
  If EV > PV, the project is ahead of schedule
  If EV < PV, the project is behind schedule
To calculate an estimate of how far ahead or behind schedule the project is
PV - EV
Avg. EV (to-date)

## Slide 19: Example: Approximating the Schedule Status
Given:
Therefore:
The project is currently behind by
PV - EV
Avg. EV (to-date)
=
54.3 – 31.2
31.2 / 6
=
4.4 weeks
 | Planned Value (PV) | Earned Value (EV)
Week 6 | 5.6 | 5.6
To Date | 54.3 | 31.2

## Slide 20: Estimating the Project Completion Date
To estimate the project completion date
  Determine the EV required to complete the project.
  Calculate the rate at which the team is accumulating EV.
  Determine how long it will take the team to earn the remaining EV.

## Slide 21: Example: Estimating Project Completion Date
Given:
 | Planned Value (PV) | Earned Value (EV)
Week 6 | 5.6 | 5.6
To Date | 54.3 | 31.2
Therefore:
Amount of EV yet to earn on project:
100 – 31.2 = 68.8 EV
Remaining estimated time in project:
68.8 / 5.2 = 13.2 weeks
Estimated week for completion:
6 + 13.2 = 19.2 weeks
The EV rate thus far is:
31.2 / 6 = 5.2 EV per week

## Slide 22: Assumptions of the EV Method
The EV method assumes that
  the plan is reasonably accurate
  the rate of task completion in the future will be roughly the same as what it was in the past
  actual project resources will be available as planned
    if staffing level increases, the EV projections will be pessimistic
    if staffing level decreases, the EV projections will be optimistic

## Slide 23: Earned Value Example
What is the schedule status?
Cumulative PV
Percent Planned or Earned Value
Cumulative EV

## Slide 24: Why Is the Team Behind?
In the last example the team might be behind for one or more of the following reasons:
  Team members aren’t working the number of task hours that were estimated in the plan.
  Effort for some or all tasks has been underestimated.
  Change requests come in that must be processed.
  Task(s) were mistakenly omitted during the launch that needed to be executed, but they weren’t added to the plan.
  An external dependency does not come in on time.

## Slide 25: Accurate Data is Key
The key to keeping commitments is to promptly detect schedule slips as soon as they occur.
With the TSP, one-day schedule slips can be recognized.
  Team members make personal plans with their work broken into tasks that require less than a week’s worth of effort.
  Plan status is based on data that is collected in real time by team members
    task time (while executing a task)
    task complete time
  Data is accurate when team members conduct their work with process discipline.

## Slide 26: Test Your Understanding
Current status can be assessed by comparing the actual earned value to date with the planned earned value to date.
Using these values, answer the following questions:
Is the team ahead or behind schedule?
How far ahead or behind?
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Earned value this cycle to date | 43.6 | 34.5 | 1.3 | 9.1

## Slide 27: Example: Determining Current Status
In this example, the team has completed 34.5% of the work after nine weeks, so the average EV burn rate is
Therefore, the project is behind by
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Earned value this cycle to date | 43.6 | 34.5 | 1.3 | 9.1

## Slide 28: Investigating the Source of Schedule Deviation
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
Four TSP measures can help you understand what might be causing schedule deviation.

## Slide 29: Checking Effort Growth
The Baseline task hours represent the total number of estimated task hours when the plan was baselined, usually at the launch.
The Current plan hours represent the total number of estimated task hours in the current plan.
The Percent Change is the percent increase or decrease in task hours since the plan was baselined. In the example above, task hours have increased by:
 | Task Hours
Baseline | 660.8
Current | 745.5
Percent Change | 12.8%

## Slide 30: Investigating the Source of Schedule Deviation
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
Three TSP measures can help you understand what might be causing the deviation.

## Slide 31: Task Hours
Task time represents direct time actually spent on tasks that are in the plan.
Analyzing the actual vs. plan schedule hours can sometimes help explain schedule deviations.
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2
In this example, by week 9, the team has applied 229.9 less hours to the work than they had planned.

## Slide 32: To-Date Hours for Tasks Completed
Comparing the actual value to the planned value provides an indicator of task effort estimation accuracy.
The ratio, plan/actual is an indicator of schedule growth due to over-estimation or underestimation of task effort. A ratio close to 1 indicates that overall, the task effort estimates are balanced between overestimates and underestimates.
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2

## Slide 33: To-Date Hours for Tasks Uncompleted
To-Date Hours for tasks uncompleted denotes total task time that has accumulated for uncompleted tasks. This represents work-in-progress.
To-date hours for tasks uncompleted is an indictor of unrealized earned value.
An excessive value for this measure may indicate possible problems with how the tasks have been set up.
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2

## Slide 34: Unrealized Earned Value
Week 9 | Plan | Actual | Plan/Actual | Plan - Actual
Earned value this cycle to date | 43.6 | 34.5 | 1.3 | 9.1
Task hours to date | 1777.0 | 1547.1 | 1.2 | 229.9
To-date hours for tasks completed | 1323.8 | 1279.3 | 1.0 | 44.5
To-date hours for tasks uncompleted | 454.0 | 267.8 | 1.7 | 186.2
Unrealized EV =
(To-date hours for tasks uncompleted) * (EV per task hour)
Potential EV =
267.8 * (34.5 / 1279.3)
Potential EV =
267.8 * 0.03 = 7.2 EV (tied up in uncompleted tasks)
Unrealized EV can sometimes provide an explanation for some of the difference between planned value (PV) and earned value (EV).

## Slide 35: Possible Problems With Task Set-Up
A large number of task hours for unfinished tasks could also indicate a problem with the schedule or with the implementation.
This value of to-date hours for tasks uncompleted should be less than about 1.5 weeks per team member. If not, then it is possible that
  some tasks are too large; tasks should be set up so that they are less than approximately one week in duration
  task(s) are not being completed because of one or more dependencies on other tasks

## Slide 36: Project End Date
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date
Are adjustments needed to optimize project completion?

## Slide 37: Project End Dates
Baseline: project completion date for the baselined plan
Current Plan: project completion date for the current plan
Predicted: project completion date given the current load balancing among team member
 | Project End Dates
Baseline | 3/19/2012
Current Plan | 3/26/2012
Predicted | 7/30/2012

## Slide 38: Predicted End Date
Predicted project end date is the date the project will end based on the latest calendar date that a team member completes their work.
 | Project End Dates
Baseline | 3/19/2012
Current Plan | 3/26/2012
Predicted | 7/30/2012
Each of the TSP support tools provides features that facilitate workload balancing among team members.
If the workload of the team is not balanced, the team’s predicted end date will be suboptimal.

## Slide 39: A Quick Way to Estimate Predicted End Date
An approximate (and optimistic) estimate of a balanced plan predicted end date can be achieved by dividing the number of hours of work remaining by the average team hours worked per week.
To obtain a more accurate earned-value-based predicted end date from the TSP tool, have the team members work together to balance the workload.
Have the planning manager and coach review the individual plans for any anomalies with respect to the predicted end date.

## Slide 40: Section Summary
In this section, we explored a number of project status indicators that can help you understand the status of your project.
Earned value status
Effort growth
Task hours
To-date hours for completed tasks
To-date hours for uncompleted tasks
Project end date

## Slide 41: Interpreting Team Data Exercise
Read the instructions.
Complete the exercise in 40 minutes.
Be prepared to share your results.