## CM
Configuration Management
Revision | Date | Author | Description
0.1 | 2005-07-26 | JPE | initial prototype release
0.2 | 2005-09-14 | JPE | added CM changed drivers to match TR improved macro functions and added comments
1 | 2006-04-24 | JPE | product release
1.01 | 2006-05-08 | JPE | added "increasing risk" annotations
1.02 | 2006-08-14 | JPE | added "Supplier Assurance" worksheet
1.03 | 2006-08-15 | SMK | updated TR number, copyright date, and reordered tabs to match TR
end | end | end | end
NOTE: add new versions by inserting a row before that marked "end"
Administrative
Weight
None
Weak
Medium
Strong

## Instructions
ACQUISITION STRATEGY DEVELOPMENT TOOL
PURPOSE
The purpose of the ACQUISITION STRATEGY DEVELOPMENT TOOL (ASDT) is to help the government program offices:
1. understand the components of an acquisition strategy
2. understand the driving factors that impact their acquisition programs
3. develop and acquisition strategy that addresses the major risks posed by these program drivers
AUDIENCE
The ASDT was developed for use by the acquisition program manager and/or program office staff. To make effective use of the ASDT, the user must have a detailed knowledge of
1. government acquisition processes and regulations
2. the scope and characteristics of the subject acquisition project
3. the capabilities of the program office
NEED
An acquisition program is subject to numerous influences, both internal and external to the program. Some influences, such as budget constraints, schedule constraints, and performance requirements are well quantified and easily understood. Other influences, such as stakeholder agreement, requirements stability, and contractor capability, are more difficult to assess and less obvious. These influences, or program drivers, are sources of risk to an acquisition program.
An acquisition strategy is one tool available to the program manager to mitigate some of these risks. An acquisition strategy is comprised of a collection of strategy elements. Each strategy element is a decision or a plan on how to proceed with a specific aspect of the program execution. Examples of strategy elements include the acquisition approach, contract approach, and competition.
Development of an acquisition strategy is not a well-understood process. In most cases, it is done in an ad hoc manner, without due consideration of the internal and external driving factors of the project. In formulating an acquisition strategy, the program manager must balance many conflicting objectives, choosing a strategy that addresses some and ignores others. This tool is a means to methodically evaluate candidate acquisition strategies in the context of the conflicting factors driving an acquisition program.
INSTRUCTIONS FOR USE
STRUCTURE OF THE ASDT
The ASDT is arranged by acquisition strategy element. Each element has an individual worksheet in the workbook. Strategy elements addressed in this tool include:
· Acquisition Approach · Competition · Contract Approach · Source of Support · Training · Solicitation ● Supplier Assurance
For each strategy element, the worsksheet lists up to eight choices for strategies and 28 program drivers. The strategies are mapped to a "strategy slider bar," followed by the drivers listed with their own "driver slider bar" (see below).
STRATEGIES
[5 empty] | 1 | <strategy 1>
[5 empty] | 2 | : |  |  |  | : | :
[5 empty] | : | <strategy 7>
[5 empty] | 8 | <strategy 8> | [5 empty] | . . .
| DRIVER |  | RANGE
| <driver 1> |  | High |  | Low |  | High | [5 empty] | Low
| <driver 2> |  | Few |  | Many |  | Many | [5 empty] | Few
[8 empty] | : |  |  |  | : |  | :
| <driver n> |  | Weak |  | Strong |  | Weak | [5 empty] | Strong
Not all drivers influence all strategy elements; however, all are included for purposes of generality, and also to encourage the program manager to consider whether or not they are applicable in this particular project.
STEP 1: Read the SEI Technical Report
Read Techniques for Developing an Acquisition Strategy by Profiling Software Risks (CMU/SEI-2006-TR-002) to gain an understanding of the process implemented in this tool. This technical report is available on the SEI Publications Web site at http://www.sei.cmu.edu/publications/publications.html.
NOTE: Spreadsheet convention - most cells on the spreadsheet are locked and protected. Only those cells with a yellow background may be accessed for data entry
STEP 2: Evaluate the drivers
On the "Driver Assessment" worksheet, evaluate each of the drivers within the range defined by the endpoints. Place an "X" in the cell that represents your best judgement of the characteristics of your program (see below).
| DRIVER |  | RANGE
| <driver 1> |  | High |  | Low |  | High |  |  |  | X |  | Low
Cell formatting will automatically color the cell background.
STEP 3: Define Strategy Element Options
For the selected strategy element, define up to eight strategy element options in cells C6 through F21. List the options from top to bottom in order of increasing capability to mitigate risk.
STEP 4: Orient the Driver Endpoints
Each driver has a defined range of values. Assign the endpoint producing the lowest risk to the left side of the slider bar, and the endpoint producing the greatest risk to the right side of the slider bar. Spreadsheet macros are provided to assist with this activity (see below).
1. Select the yellow cell (Column H) in the row for the driver slider bar.
2. Ctrl-Shft-L assigns the first endpoint to the left side of the driver bar.
3. Ctrl-Shft-R assigns the first endpoint to the right side of the driver bar.
4. Ctrl-Shft-X erases both endpoints for the driver bar.
| DRIVER |  | RANGE |  | WEIGHT
| <driver 1> |  | High | Low |  |  |  | High |  |  |  |  | Low
| DRIVER |  | RANGE |  | WEIGHT
| <driver 1> |  | High | Low |  |  |  | Low |  |  |  |  | High
| DRIVER |  | RANGE |  | WEIGHT
| <driver 1> |  | High | Low
STEP 5: Transfer Driver Evaluations
Transfer the driver evaluations captured on the "Driver Assessment" worksheet to the current strategy worksheet. A spreadsheet macro (Ctrl-Shft-E) is available to accomplish this.
1. Select the desired strategy worksheet.
2. Ctrl-Shft-E transfers all evaluations from the "Driver Assessment" worksheet based upon the assignments made for the endpoints.
STEP 6: Choose a Strategy
After all drivers are assessed, examine the resulting worksheet. The horizontal distance between the driver assessment and the chosen strategy represents the risk and/or opportunity presented by that driver in the context of the chosen strategy. Several alternative methods may be used in selecting a strategy to address the drivers.
1. | Choose a strategy for maximum alignment with the assessed drivers (Strategy A).
[5 empty] | High |  |  | X |  |  |  |  | Low
2. | Choose a strategy that addresses the driver of greatest importance, or adding the greatest risk (Strategy B). |  |  |  | Many |  |  |  | X |  |  |  | Few
[5 empty] | Many | [6 empty] | X | Few
[6 empty] | : | [5 empty] | : |  | :
[5 empty] | Weak |  |  |  |  | X |  |  | Strong
A spreadsheet macro is available to assist in the selection of a strategy.
1. Within the strategy bar, select the cell representing the chosen strategy.
2. Ctrl-Shft-S marks the chosen strategy in the strategy and the driver bars.
3. Choosing a cell in a column to the left or right of the slider bars and pressing Ctrl-Shft-S clears all driver bars.
STEP 7: Evaluate residual risks
For the chosen strategy, examine the drivers that are not well-aligned with the strategy. These are the drivers that are not being addressed by the acquisition strategy. They inject risk/opportunity into the program, and must be addressed by risk management methods other than the acquisition strategy. Evaluate these risks to determine the ability of the program to address them. Develop mitigation plans as needed.
ADDING WORKSHEETS FOR NEW STRATEGY ELEMENTS
A separate worksheet is included for each strategy element. New worksheets can be generated for additional strategy elements as follows:
a. Click Tools > Protection > Unprotect Workbook. (no password required)
b. Click Insert > Worksheet to create a new worksheet.
c. Click the tab for the "Template" worksheet. Click Tools > Protection > Unprotect Sheet. (no password required)
d. Select the entire worksheet by clicking the top left corner of the row and column headers. Copy the contents of the worksheet by clicking Edit > Copy.
e. Select cell A1 on the newly created worksheet and click Edit > Paste.
f. Click and drag the new worksheet tab to a location to the right of the "Driver Assessment" worksheet. This is necessary for the macros to work properly.
g. Double click on the tab for the new worksheet tab and change the worksheet name to something representative of the desired strategy element.
h. Enter the strategy element name at the top of the worksheet.
i. Click Tools > Protection > Protect Sheet. (do not enter a password)
j. Click Tools > Protection > Protect Workbook. (do not enter a password)
k. To evaluate the new strategy element, repeat STEPS 3 through 7 as described above.
AUTHORS
Authors of this product are: Mary Catherine Ward Software Engineering Institute, Carnegie Mellon University Joseph Elm Software Engineering Institute, Carnegie Mellon University Susan Kushner Software Engineering Institute, Carnegie Mellon University
REFERENCES
For a detailed discussion of the theory and application of acquisition strategy development, see the following technical report at http://www.sei.cmu.edu/publications/publications.html:
Ward, Mary Catherine; Elm, Joseph; & Kushner, Susan. Techniques for Developing an Acquisition Strategy by Profiling Software Risks (CMU/SEI-2006-TR-002). Pittsburgh, PA: Software Engineering Institute, Carnegie Mellon University, 2006.
Version: |  | 1.03 |  | Date: | 2006-08-15 | [9 empty] | © 2006 by Carnegie Mellon University
Ctrl-Shft-L
Ctrl-Shft-R
select this cell, then execute the macros
Strategy Bar
Driver Bar
Strategy A
Strategy B
Most important / highest risk driver
Ctrl-Shft-X

## License & Disclaimers
ACQUISITION STRATEGY DEVELOPMENT TOOL v0.01
LICENSE AND DISCLAIMERS
This work is sponsored by the U.S. Department of Defense, and was performed by Carnegie Mellon University (Carnegie Mellon) through its Software Engineering Institute (SEI) . The SEI is a federally funded research and development center sponsored by the U.S. Department of Defense.
Copyright 2006 by Carnegie Mellon University.
Permission is hereby granted, free of charge, to any person obtaining a copy of this software and associated documentation files (the “Software”), to deal in the Software without restriction, including without limitation the rights to reproduce and use “as is” the Software under the following conditions:
The above copyright notice and this permission notice shall be included in all copies or substantial portions of the Software.
NO WARRANTY
ANY LICENSED SOFTWARE IS PROVIDED ON AN “AS IS” BASIS. CARNEGIE MELLON MAKES NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, AS TO ANY MATTER INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR A PARTICULAR PURPOSE, OR MERCHANTABILITY, EXCLUSIVITY OR RESULTS OBTAINED FROM LICENSEE’S USE OF ANY INTELLECTUAL PROPERTY DEVELOPED UNDER THIS AGREEMENT, NOR SHALL ANY PARTY HERETO BE LIABLE TO THE OTHER FOR INDIRECT, SPECIAL, OR CONSEQUENTIAL DAMAGES SUCH AS LOSS OF PROFITS OR INABILITY TO USE SAID INTELLECTUAL PROPERTY OR ANY APPLICATIONS AN/OR DERIVATIONS THEREOF.
CARNEGIE MELLON MAKES NO WARRANTY OF ANY KIND WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT, INFRINGEMENT, OR THEFT OF TRADE SECRETS AND DOES NOT ASSUME ANY LIABILITY HEREUNDER FOR ANY INFRINGEMENT OF ANY PATENT, TRADEMARK, OR COPYRIGHT ARISING FROM THE USE OF THE DELIVERABLES, INFORMATION, INTELLECTUAL PROPERTY, OR OTHER PROPERTY OR RIGHTS GRANTED TO IT OR PROVIDED BY IT HEREUNDER. LICENSEE AGREES THAT IT WILL NOT MAKE ANY WARRANTY ON BEHALF OF CARNEGIE MELLON EXPRESSED OR IMPLIED, TO ANY PERSON CONCERNING THE APPLICATION OF OR THE RESULTS TO BE OBTAINED WITH THE SOFTWARE UNDER THIS AGREEMENT.
CARNEGIE MELLON INDEMNIFICATION
Licensee hereby agrees to defend, indemnify, and hold harmless Carnegie Mellon, its trustees, officers, employees, and agents from all claims or demands made against them (and any related losses, expenses, or attorney’s fees) arising out of, or relating to licensee’s negligent use or willful misuse of or negligent conduct or willful misconduct regarding Carnegie Mellon Intellectual Property, facilities, or other rights or assistance granted by Carnegie Mellon under this Agreement, including, but not limited to, any claims of product liability, personal injury, death, damage to property, or violation of any laws or regulations.
EXTERNAL USE
Request for permission for any other use should be sent to permission@sei.cmu.edu.
This work was created in the performance of Federal Government Contract Number FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center. The Government of the United States has a royalty-free government-purpose license to use, duplicate, or disclose the work, in whole or in part and in any manner, and to have or permit others to do so, for government purposes pursuant to the copyright license under the clause at 252.227-7013.
Version: | 1.03 | Date: | 2006-08-15 | © 2006 | © 2005 by Carnegie Mellon University

## Template
STRATEGY ELEMENT:
STRATEGIES
1
2
3
4
5
6
7
8
Strategy Slider Bar
Increasing risk mitigation capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 2: Assign endpoints for each of the relevant drivers

## Driver Assessment
STRATEGY DRIVER ASSESSMENT | [5 empty] | Type an "X" in the box that represents your evaluation for each driver (one "X" per row).
STRATEGY DRIVER |  |  | RANGE |  |  | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High | Very Low |  |  | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High | Low |  |  | High
|  | Supplier Availability | Low | High | Low |  |  | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid | Flexible |  |  | Rigid
|  | Funding Constraints | Few | Many | Few |  |  | Many
|  | Funding Profile | Mismatched | Matched | Mismatched |  |  | Matched
|  | Schedule Constraints | Few | Many | Few |  |  | Many
|  | Urgency | Low | High | Low |  |  | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong | Weak |  |  | Strong
|  | PMO Staff Capacity | Inadequate | Adequate | Inadequate |  |  | Adequate
|  | PMO Staff Stability | Low | High | Low |  |  | High
|  | PMO Process Focus | Weak | Strong | Weak |  |  | Strong
| Stakeholders | Number and Diversity | Small | Large | Small |  |  | Large
|  | Level of Engagement | Low | High | Low |  |  | High
|  | Level of Agreement | Low | High | Low |  |  | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong | Weak |  |  | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate | Inadequate |  |  | Adequate
|  | Supplier Staff Stability | Low | High | Low |  |  | High
|  | Supplier Performance to | Poor | Excellent | Poor |  |  | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High | Low |  |  | High
|  | Requirements | Low | High | Low |  |  | High
Understanding
|  | Quality Attribute | Low | High | Low |  |  | High
Definition Quality
|  | Interoperability | Simple | Complex | Simple |  |  | Complex
| Architecture and Design | Precedence | Low | High | Low |  |  | High
|  | Quality Attribute | Low | High | Low |  |  | High
Constraints
|  | Technology Readiness | Immature | Mature | Immature |  |  | Mature
|  | Legacy Considerations | Low | High | Low |  |  | High
|  | COTS / GOTS / Reuse | Low | High | Low |  |  | High
| Implementation and Test | Test Environment | Low | High | Low |  |  | High
Complexity
|  | Test Environment | Low | High | Low |  |  | High
Availability
|  | Number of System | Few | Many | Few |  |  | Many
Configurations
| Deployment | Number of Sites | Few | Many | Few |  |  | Many
|  | User Readiness | Low | High | Low |  |  | High
|  | Maintainer Readiness | Low | High | Low |  |  | High
|  | Transition / Data Migration | Low | High | Low |  |  | High
| Maintenance and Support | Number of System | Few | Many | Few |  |  | Many
Configurations
|  | Update Readiness | Low | High | Low |  |  | High
|  | Support Duration | Short | Long | Short |  |  | Long
|  | Re-Competition Readiness | Low | High | Low |  |  | High
|  | Operational Environment | Benign | Harsh | Benign |  |  | Harsh
|  | Legacy Considerations | Low | High | Low |  |  | High
|  | Complexity of Data Rights | Low | High | Low |  |  | High
| Disposal |  | Unrestricted | Restricted | Unrestricted |  |  | Restricted
Version: |  | 1.03 | Date: | 2006-08-15 |  |  | © 2006 by Carnegie Mellon University

## Acquisition Approach
STRATEGY ELEMENT: |  |  | Acquisition Approach
STRATEGIES
1 | Evolutionary/Spiral
2
3
4 | Evolutionary/Incremental
5
6
7 | Single-Step
8
Strategy Slider Bar
Increasing Risk Mitigation Capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 2: Assign endpoints for each of the relevant drivers

## Solicitation
STRATEGY ELEMENT: |  |  | Solicitation
#REF!
STRATEGIES | [9 empty] | #REF!
1 | Invitation for Bid (IFB) | [8 empty] | #REF!
#REF!
2 | [9 empty] | #REF!
3 | Request for Proposal (RFP) with SOW
4
5 | Request for Proposal (RFP) with SOO
6
7 | Request for Quotation (RFQ)
8
Strategy Slider Bar
Increasing Risk Mitigation Capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 2: Assign endpoints for each of the relevant drivers
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet

## Contract Approach
STRATEGY ELEMENT: |  |  | Contract Approach
#REF!
STRATEGIES | [9 empty] | #REF!
1 | Firm-Fixed-Price, Level-of-Effort Term Contract | [8 empty] | #REF!
#REF!
2 | Firm-Fixed-Price (FFP) Contract | [8 empty] | #REF!
3 | Fixed-Price Incentive Contract
4 | Fixed-Price Contract With Award Fees
5 | Cost-Sharing Contract
6 | Cost-Plus-Fixed-Fee Contract
7 | Cost-Plus-Incentive-Fee Contract
8 | Cost-Plus-Award-Fee Contract
Strategy Slider Bar
Increasing Risk Mitigation Capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet
STEP 2: Assign endpoints for each of the relevant drivers
STEP 1: Complete driver assessments on "Driver Assessment" worksheet

## Competition
STRATEGY ELEMENT: |  |  | Competition
STRATEGIES
1 | Full and Open Competition
2
3
4 | Full and Open Competition After Exclusion of Sources
5
6
7 | Sole Source Contracting
8
Strategy Slider Bar
Increasing Risk Mitigation Capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 2: Assign endpoints for each of the relevant drivers
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet

## Supplier Assurance
STRATEGY ELEMENT: |  |  | Supplier Assurance
STRATEGIES
1 | No COTS or F/OS Products; All Software Developed by Cleared U.S. Sources
2
3 | No COTS or F/OS Products; All Software Developed by U.S. Sources
4
5 | Use COTS and F/OS Products Only from Trusted Sources
6 | Evaluate COTS and F/OS Products Before Incorporation
7
8 | Use COTS and F/OS Products Freely
Strategy Slider Bar
Increasing risk mitigation capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 2: Assign endpoints for each of the relevant drivers
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 2: Assign endpoints for each of the relevant drivers

## Training
STRATEGY ELEMENT: |  |  | Training
#REF!
STRATEGIES | [9 empty] | #REF!
1 | Self-Training | [8 empty] | #REF!
#REF!
2 | [9 empty] | #REF!
3 | Computer-Based Training
4
5 | Distance Learning
6
7 | Classroom Training
8 | Field Training
Strategy Slider Bar
Increasing Risk Mitigation Capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 2: Assign endpoints for each of the relevant drivers
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet

## Source of Support
STRATEGY ELEMENT: |  |  | Source of Support
#REF!
STRATEGIES | [9 empty] | #REF!
1 | Contractor Logistics Support | [8 empty] | #REF!
#REF!
2 | [9 empty] | #REF!
3 | PMO Support
4
5 | Depot Support
6
7 | Indigenous Support
8
Strategy Slider Bar
Increasing Risk Mitigation Capability
STRATEGY DRIVER |  |  | RANGE |  | WEIGHT | Driver Slider Bars
Software Criticality |  |  | Very Low | Very High
Acq. Envir. Category |  | Policies and Mandates | Low | High
|  | Supplier Availability | Low | High
Programmatic Category |  | Mission Needs and Scope | Flexible | Rigid
|  | Funding Constraints | Few | Many
|  | Funding Profile | Mismatched | Matched
|  | Schedule Constraints | Few | Many
|  | Urgency | Low | High
Organizational Category | PMO Capability | PMO Staff Skills | Weak | Strong
|  | PMO Staff Capacity | Inadequate | Adequate
|  | PMO Staff Stability | Low | High
|  | PMO Process Focus | Weak | Strong
| Stakeholders | Number and Diversity | Small | Large
|  | Level of Engagement | Low | High
|  | Level of Agreement | Low | High
| Supplier Capability | Supplier Staff Skills | Weak | Strong
|  | Supplier Staff Capacity | Inadequate | Adequate
|  | Supplier Staff Stability | Low | High
|  | Supplier Performance to | Poor | Excellent
Date
Life Cycle Category | Product Definition and Specification | Requirements Volatility | Low | High
|  | Requirements | Low | High
Understanding
|  | Quality Attribute | Low | High
Definition Quality
|  | Interoperability | Simple | Complex
| Architecture and Design | Precedence | Low | High
|  | Quality Attribute | Low | High
Constraints
|  | Technology Readiness | Immature | Mature
|  | Legacy Considerations | Low | High
|  | COTS / GOTS / Reuse | Low | High
| Implementation and Test | Test Environment | Low | High
Complexity
|  | Test Environment | Low | High
Availability
|  | Number of System | Few | Many
Configurations
| Deployment | Number of Sites | Few | Many
|  | User Readiness | Low | High
|  | Maintainer Readiness | Low | High
|  | Transition / Data Migration | Low | High
| Maintenance and Support | Number of System | Few | Many
Configurations
|  | Update Readiness | Low | High
|  | Support Duration | Short | Long
|  | Re-Competition Readiness | Low | High
|  | Operational Environment | Benign | Harsh
|  | Legacy Considerations | Low | High
|  | Complexity of Data Rights | Low | High
| Disposal |  | Unrestricted | Restricted
Increasing Risk
Version: |  | 1.03 | Date: | 2006-08-15 |  |  |  |  | © 2006 by Carnegie Mellon University
Ctrl-Shft-L
Ctrl-Shft-R
Ctrl-Shft-X
blank
STEP 1: Complete driver assessments on "Driver Assessment" worksheet
STEP 2: Assign endpoints for each of the relevant drivers
STEP 4: Select cell for chosen strategy and press Ctrl-Shft-S
STEP 3: Press Ctrl-Shft-E to transfer driver evaluations from "Driver Assessment" worksheet